## Platform-Summary-Category
Category | (All)
Product Component | (All)
SBU | (All)
Sum of Effort | Column Labels
Row Labels | 2223-Q4 | 2324-Q1 | TBD | Grand Total
Customer-Specific | 18.85 | 2.6 | 52 | 73.45
Dev-Productivity | 26.65 | 26 | 17.55 | 70.2
Tech-Initiative | 19.5 |  | 55.9 | 75.4
Tech-Upgrade | 2.6 | 2.6 | 12.35 | 17.55
Grand Total | 67.6 | 31.2 | 137.8 | 236.6
Supply
No of Resources | 17
Capacity(80% availability) | 40.8
Deep Tech Support | 8.16
Build Capacity | 32.64
Excess/Shortage | -34.96

## Platform-Summary-SBU
Product Component | (All) |  |  | Supply | 18 | 43.2
Sum of Effort | Column Labels
Row Labels | 2223-Q4 | 2324-Q1 | TBD | Grand Total
AVN | 18.2 | 26 | 8.45 | 52.65
CTB |  |  | 3.9 | 3.9
RTB | 18.2 | 26 | 4.55 | 48.75
ERP | 11.7 |  | 20.8 | 32.5
HRP | 13 | 2.6 | 26.65 | 42.25
LGT | 6.5 |  | 3.9 | 10.4
PCO |  |  | 7.8 | 7.8
TECH | 18.2 | 2.6 | 70.2 | 91
Grand Total | 67.6 | 31.2 | 137.8 | 236.6

## Platform-Summary-Subfunction
Status | (Multiple Items) |  |  | Supply | 18 | 43.2
Sum of Effort | Column Labels
Row Labels | 2223-Q4 | 2324-Q1 | TBD | Grand Total
Audit Trial |  |  | 2.6 | 2.6
InBox | 2.6 |  | 6.5 | 9.1
InBox Montior |  |  | 1.95 | 1.95
MDCF | 3.9 | 2.6 | 13 | 19.5
Platform | 34.45 | 26 | 39 | 99.45
Reporting | 14.95 |  | 30.55 | 45.5
AVN | 0.65 |  |  | 0.65
ERP |  |  | 8.45 | 8.45
RTB |  |  | 8.45 | 8.45
HRP | 4.55 |  | 1.95 | 6.5
LGT | 4.55 |  | 1.3 | 5.85
TECH | 5.2 |  | 18.85 | 24.05
Workflow | 11.05 | 2.6 | 24.7 | 38.35
Grand Total | 66.95 | 31.2 | 118.3 | 216.45

## Platform
Tech ID | Category | Product Component | Theme | EPIC | User Story Details | SBU | Projects | Priority | Benefit | Size | Effort | Score | Plan Quarter | Release Month | Status | Remarks | Delivery Owner | ProgressNote
| RTB | Platform | Customer-Specific | Code Generators | Java Code Generator Changes for ListEdit | AVN | 1 | High | Medium | M | 1.3 | 4.6 | 2223-Q4 | 2023-01-01 | Hold
| RTB | Platform | Tech-Initiative | Code Generators | Evolv code generation integration in mainstream code generator | TECH | 2 | High | High | M | 1.3 | 6 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Usablity | Hide the links which are not applicable - (ex: eZeeView) | AVN | 2 | Medium | Medium | M | 1.3 | 4.6 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-73518 - Validation for default values of segment data items and method parameters | AVN | 4 | High | Very High | S | 0.65 | 6 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-72956 - Validation to restrict hidden view definition for list edit, multi select combo controls | AVN | 4 | High | Very High | M | 1.3 | 6 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-72725 - Validation to restrict work request publish when no columns are defined for listedit controls | AVN | 4 | Medium | High | S | 0.65 | 9 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-69657 - List loading - System allowed to map the single segment dataitem for list view control. But it should allow only for multi segment data items. | AVN | 4 | Medium | Medium | S | 0.65 | 8.2 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-69420 - Codegen failed due to invalid control attribute mapping. System is not validated this invalid control attribute mapping in publish ECR | AVN | 4 | Medium | Medium | S | 0.65 | 8.2 | 2223-Q4 | 2023-01-01 | Completed
| RTB | MDCF | Tech-Initiative | Bulk Service Executor | Bulk service executor - Provision to enable data source as application table | HRP | 4 | Very High | Very High | M | 1.3 | 7 | 2223-Q4 | 2023-02-01 | Completed
| RTB | MDCF | Tech-Initiative | Bulk Service Executor | Bulk service executor - Provision to schedule jobs thru Dameon | HRP | 4 | Very High | Very High | M | 1.3 | 7 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Reporting | Customer-Specific | Security | KPMG - Insufficient Code Cleansing - (Low) | HRP | 4 | Medium | Low | S | 0.65 | 7 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Reporting | Customer-Specific | Security | SCOGEN - Using Componentes with Known Vulnerabilities – Latest version is not available for jquery, jqueryUI - (Medium) | HRP | 4 | Medium | Medium | M | 1.3 | 6.6 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Reporting | Customer-Specific | Security | TOLL - Reflected Cross Site Scripting (R-XSS) Attack - (Medium) | HRP | 4 | Medium | Medium | M | 1.3 | 6.6 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Workflow | Customer-Specific | Scheduler | Decoupling daemon for time-based workflow | HRP | 1 | High | High | L | 1.95 | 4 | 2223-Q4 | 2023-02-01 | Completed | Beta Inprogress with HRP
| RTB | Reporting | Customer-Specific | Security | CSP Changes for Reporting Components - Phase-2 | LGT | 1 | Very High | High | L | 1.95 | 5 | 2223-Q4 | 2023-02-01 | In Progress | Targetted to close by End Mar
| RTB | Reporting | Tech-Initiative | Packaging | Verification of Infra components for RT Package 2.10.0.0 | TECH | 4 | Very High | Very High | S | 0.65 | 7 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Reporting | Customer-Specific | Browser Support | Drill Through Report in Chrome Browser | AVN | 4 | Medium | Very High | S | 0.65 | 5 | 2223-Q4 | 2023-01-01 | In Progress
| RTB | Reporting | Dev-Productivity |  | Provision to share generated reports to ftp instead of sftp | LGT | 4 | Medium | Medium | S | 0.65 | 8.2 | 2223-Q4 | 2023-01-01 | Cancelled | Feature avaialble , SBU to respond and plan again if required
| RTB | Reporting | Tech-Initiative | Logging | Feasibility for enabling logs in jasper reporting engine | TECH | 2 | Medium | Medium | S | 0.65 | 6.2 | 2223-Q4 | 2023-02-01 | In Progress
| RTB | Reporting | Dev-Productivity | Documentation | Reports - devs hard code logos, should come from configuration | LGT | 1 | Medium | Medium | S | 0.65 | 5.2 | 2223-Q4 | 2023-02-01 | Completed | Approach document in progress
| CTB | Platform | Tech-Initiative | Ramco Developer Studio | Ramco Developer Studio - Low code platform - Phase-1 | TECH | 4 | High | Very High | XXL | 3.9 | 6 | 2223-Q4 | 2023-01-01 | In Progress
| RTB | Platform | Dev-Productivity | UI Control | Provision to specify ShowHistogram property for Gantt Controls | ERP | 4 | Medium | Medium | M | 1.3 | 6.6 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-69282 - List view modelling is incomplete. LVWMHI_Symbolcode_Combo is involved in publication dataitem which should not be done. System allowed to publish the ECR and not validated. | AVN | 4 | High | Medium | S | 0.65 | 9.2 | 2223-Q4 | 2023-01-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-71003 - Codegen is getting continuously failed for BASWC component. activity :-WCRwCapCer ; ui:-AdvanceSearch ; section :- RwAsJqurSec control synonym :-RwAs_RulesR in this UI there is a improper rulebuilder control which has no definition of grid and header grid columns. System allowed to publish ECR without definition for grid in rule builder. | AVN | 4 | Medium | Medium | S | 0.65 | 8.2 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-70182. Codegen is getting Failed Continuously For BASCONFIG component. Issue resolved after changed the parameter mapping for the service "cfg_mqr_fet_ser" | AVN | 4 | Medium | High | S | 0.65 | 9 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Platform | Dev-Productivity | Validations | TECH-67993 – Handle changes. : Length of BT Synonym caption exceeded 60 characters. ECR is validated successfully. | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2223-Q4 | 2023-02-01 | Pending
| RTB | Platform | Dev-Productivity | Training | Understanding Issue - Method Documentation | AVN | 1 | Low | Low | S | 0.65 | 3.5 | 2223-Q4 | 2023-02-01 | Pending
| RTB | Platform | Dev-Productivity | Training | Session for understanding width definition for grid columns | AVN | 1 | Medium | Low | S | 0.65 | 4 | 2223-Q4 | 2023-02-01 | Pending
| RTB | Platform | Dev-Productivity | Training | Session for understanding data column and label column width | AVN | 1 | Medium | Low | S | 0.65 | 4 | 2223-Q4 | 2023-02-01 | Pending
| RTB | Platform | Dev-Productivity | Usablity | Provision to auto re-sequence column and column group | AVN | 4 | Medium | High | L | 1.95 | 6 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Reporting | Tech-Upgrade | Logging | Log4j 2.19.0 library upgrade (Current version 2.17.0) | TECH | 4 | High | High | M | 1.3 | 8 | 2223-Q4 | 2023-03-01 | In Progress
| RTB | Reporting | Tech-Upgrade | Upgrade | Jasper (6.20) version upgrade | HRP | 4 | High | High | M | 1.3 | 8 | 2223-Q4 | 2023-03-01 | In Progress | Java upgrade dropped, Log 4J planned
| RTB | Workflow | Customer-Specific | Workflow Configurations | Enable workflow screen 1) Save to be optimized with process only modified rows (ML Save taking longer time for 700 OUs) 2) Additional filter (OU Description) to fetch ML | ERP | 4 | Medium | High | XL | 2.6 | 5.5 | 2223-Q4 | 2023-03-01 | In Progress
| RTB | Workflow | Dev-Productivity | Workflow Configurations | Next gen workflow - Provision to add clear filters under criteria tab | LGT | 4 | Medium | High | M | 1.3 | 7 | 2223-Q4 | 2023-04-01 | Yet to Start
| RTB | Reporting | Customer-Specific | Security | CSP Changes for Reporting Components - Phase-3 | LGT | 1 | Very High | High | L | 1.95 | 5 | 2223-Q4 | 2023-03-01 | In Progress
| RTB | Platform | Dev-Productivity | Mobility | Modeling and Code Generator changes for GEO FENCE (MSTD_GEOFENCE_SEC System defined section name with a multi-line control MLMSTD_GEOFENCE_CTRL ( 4 Columns - MSTD_FENCE_ID, MSTD_CENTER_LAT, MSTD_CENTER_LONG, MSTD_RADIUS) and header control (HDN_FENCE_ID) and 2 task (MSTD_GEOFENCE_CREATE & MSTD_GEOFENCE_REMOVE ) | ERP | 4 | Medium | Medium | M | 1.3 | 6.6 | 2223-Q4 | 2023-02-01 | Completed
| RTB | Platform | Dev-Productivity | File Upload | Modeling and web layer (activity dll) code generator changes for upload max file size | HRP | 4 | Medium | Medium | M | 1.3 | 6.6 | 2223-Q4 | 2023-02-01 | Completed
| CTB | Platform | Tech-Initiative | Ramco Developer Studio | Ramco Developer Studio - Low code platform - Phase-2 | TECH | 4 | High | Very High | XXL | 3.9 | 6 | 2223-Q4 | 2023-02-01 | In Progress
| CTB | Workflow | Dev-Productivity | Packaging | Delivering Workflow IS Service dlls via VwApie Framework | ERP | 4 | High | High | XL | 2.6 | 6.5 | 2223-Q4 | 2023-03-01 | Completed
| CTB | MDCF | Dev-Productivity | Bulk Service Executor | Provision to take input files from SFTP folder | ERP | 4 | High | High | M | 1.3 | 8 | 2223-Q4 | 2023-03-01 | In Progress | TI Cycles
| RTB | Reporting | Tech-Initiative | Packaging | Reporting Component - Cumulative Package and Release - DW Version - 1.1.41.0 | TECH | 4 | High | High | XL | 2.6 | 6.5 | 2223-Q4 | 2023-06-01 | Yet to Start | To conclude on Single Version Release along with .net framework 4.8 compilation
| RTB | Platform | Dev-Productivity | Validations | TECH-71164 - For Scrap parts (APSE-19498) While Publishing this ECR : SPN_ECR_00043 in (Handle Changes 5_7 Dev) error was throwing. ECR has been validated. Defect in Handle changes DB | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2223-Q4 | 2023-03-01 | Yet to Start
| RTB | Platform | Dev-Productivity | Code Generators | TECHB-926 - Provision to initiate code generation as part of publish ECR | AVN | 4 | Medium | High | L | 1.95 | 6 | 2223-Q4 | 2023-03-01 | Yet to Start
| RTB | Platform | Dev-Productivity | Code Generators | Provision to download generated code from view code generation request screen | AVN | 4 | Medium | High | M | 1.3 | 7 | 2223-Q4 | 2023-03-01 | Yet to Start
| RTB | Platform | Dev-Productivity | Usablity | Metadata clean-up for service definition - Processing type – Regular/batch? Cached Zipped?? ClearKeyPattern | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2223-Q4 | 2023-03-01 | Yet to Start
| RTB | Platform | Dev-Productivity | Preview | Provision to preview ui proto with templates, icons and tiles - Phase-1 | AVN | 4 | High | Very High | XXL | 3.9 | 6 | 2324-Q1 | 2023-04-01 | Yet to Start
| CTB | Workflow | Customer-Specific |  | HRP SAAS - Exposing Workflow configurator screen launch services as CGS (GraphQL queries) | HRP | 1 | Medium | Medium | XL | 2.6 | 2.4 | 2324-Q1 |  | Yet to Start
| CTB | Platform | Tech-Initiative | Ramco Developer Studio | Ramco Developer Studio - Low code platform - Phase-3 (POC with Tab, Grid and Template Controls) | TECH | 4 | High | Very High | XXL | 3.9 | 6 | 2223-Q4 |  | Yet to Start
| RTB | Workflow | Customer-Specific | Rejection Cycle | Workflow - Feasibility check- Rejection Cycle - Based on configuration, if a document in reinitiated and follows same path it should be routed to n-1 level instead of next level | ERP | 4 | High | High | XL | 2.6 | 6.5 | 2223-Q4 | 2023-04-01 | Yet to Start
| CTB | InBox | Customer-Specific | InBox | SASSY - InBox api's | HRP | 4 | High | High | XL | 2.6 | 6.5 | 2223-Q4 | 2023-03-01 | In Progress
| RTB | MDCF | Tech-Upgrade |  | MDCF - Upgrade for Hub version (currently it works with ext js-2 version only) | TECH | 4 | Medium | High | XL | 2.6 | 5.5 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Rollback / Undo functionality for WR, RCN and ECR | AVN | 4 | Medium | High | XXL | 3.9 | 5.3333 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | TECH-72600. Getting the mentioned error while launching handle messages-->Message Task mapping tab. Latest model SP's has been compiled. SQL Defect in Handle changes DB | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | TECH-71021 - Unable to make solutioning changes in customer ECR in HandleChanges_FS Context. Issue has been resolved after correcting the model sp. Defect in Handle changes DB | AVN | 1 | Medium | Medium | M | 1.3 | 3.6 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | TECH-69234. Unable to publish the ECR in handle changes mode. getting attached error. ECR has been validated after correcting model sp. ECR has been validated after correcting model sp | AVN | 1 | Medium | High | S | 0.65 | 6 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | TECHB-924 - Bulk validation for WR, RCN and ECR publish | AVN | 4 | High | Very High | XXL | 3.9 | 6 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | TECHB-925 - Publish ECR in offline mode (queuing) | AVN | 4 | Medium | High | XXL | 3.9 | 5.3333 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Design Service - Provision to default ilbo-control association based on BT Synonym. Replacement combo control with list edit controls | AVN | 4 | Medium | High | L | 1.95 | 6 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Smart search to choose BR Parameter data item | AVN | 4 | Medium | High | M | 1.3 | 7 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | TECHB-928 - Default value for Segment data item based on BT synonym - | AVN | 4 | Medium | Very High | S | 0.65 | 5 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Understanding Issue - Design Refinements - Default Segment Data Item Parameter mapping - Default Segment Data item UI Control mapping?? | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Understanding Issue - Segment definition - Processing Type, BO Definition, Mandatory Flag??, Combo Fill? | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Understanding Issue - Segment dataitem definition - IsPartOfKey, Mandatory Flag?? | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Understanding Issue - Process Section Rules - Connectivity Flag, [API Invocation - Specification, Path, Operation] | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Understanding Issue - Process Section - Section Type (Main, OnCommit, OnRollback) | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Understanding Issue - Define Methods - SP Message Protocol (Out Parameter, Multiple Record Set, Selected Column??) | AVN | 1 | Medium | Medium | S | 0.65 | 5.2 | 2324-Q1 |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Handle changes for workflow configuration in platform model | AVN | 1 | High | Medium | L | 1.95 | 3.8 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific | DW Classic Version | DW Classic version - Latest browser version support for DBS | ERP | 2 | Medium | Medium | XXL | 3.9 | 3.2667 | TBD |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Scan Property for Link Task | ERP | 1 | High | Medium | S | 0.65 | 6.2 | TBD |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Provision to model dynamic ILBO Caption with templates | ERP | 1 | High | Medium | M | 1.3 | 4.6 | TBD |  | Yet to Start
| CTB | Platform | Tech-Initiative |  | Platform-UDS modeling enablement - Querying from cache with aggregation, filters and sort | TECH | 4 | Medium | Very High | XL | 2.6 | 5 | TBD |  | Yet to Start
| CTB | InBox | Tech-Initiative | InBox | New InBox - Phase 1 Changes | TECH | 1 | Medium | Medium | XXL | 3.9 | 2.2667 | TBD |  | Yet to Start
| RTB | Workflow | Customer-Specific |  | Need to configure multiple From Mail Id option for Workflow / Nextgen workflow / Schedule reports for RCT Project | AVN | 2 | Medium | High | XL | 2.6 | 3.5 | TBD |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | Provision to generate filling methods for listedit, combo, charts without FlowBR | TECH | 4 | Medium | High | L | 1.95 | 6 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Glance - Quick / Combo Link | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Glance - Special Charts | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Action Items in multiple file upload | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Provision to specify dynamic width for grid columns which have dynamic caption | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative | Glance | SOLR and ES Listedit in Glance | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative | Glance | Glance modeling for bulk file download as zip file | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | MDCF | Customer-Specific |  | MDCF SSO | HRP | 4 | Low | Low | XXL | 3.9 | 4.6667 | TBD |  | Yet to Start
| RTB | MDCF | Customer-Specific |  | MDCF - UI changes for mapping same task multiple times | HRP | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific |  | OU level precision for ARI Reports | HRP | 4 | Low | Low | S | 0.65 | 6.5 | TBD |  | Defered
| RTB | Reporting | Customer-Specific | Security | Disabling FIPS compliant algorithms for encryption, hashing, and signing | ERP | 4 | Medium | Medium | XL | 2.6 | 5.4 | TBD |  | Yet to Start
| RTB | MDCF | Customer-Specific |  | MDCF LDAP | HRP | 4 | Medium | Medium | M | 1.3 | 6.6 | TBD |  | Yet to Start
| CTB | MDCF | Customer-Specific |  | MDCF for Java Tech Stack | AVN | 4 | Low | Low | XXL | 3.9 | 4.6667 | TBD |  | Yet to Start
| RTB | Reporting | Tech-Upgrade |  | Reporting - Vulnerability fixation for FOSSA observations | TECH | 4 | Medium | High | XXL | 3.9 | 5.3333 | TBD |  | Yet to Start
| RTB | Workflow | Tech-Upgrade |  | Infra - Vulnerability fixation for FOSSA observations | TECH | 4 | Medium | High | XXL | 3.9 | 5.3333 | TBD |  | Yet to Start
| RTB | Platform | Tech-Upgrade |  | Platform Web Runtime - Vulnerability fixation for FOSSA observations | TECH | 4 | Medium | High | L | 1.95 | 6 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific |  | Pivot Grid in Dcube | HRP | 4 | Medium | High | L | 1.95 | 6 | TBD |  | Yet to Start
| RTB | InBox | Customer-Specific | InBox | Provision to navigate back to InBox on successful execution of a workflow task | HRP | 1 | Medium | Medium | XL | 2.6 | 2.4 | TBD |  | Yet to Start
| RTB | Workflow | Tech-Initiative |  | Workflow mailer service deadlock / not started - consolidated report | TECH | 4 | Low | Medium | L | 1.95 | 5.3 | TBD |  | Yet to Start
| CTB | Reporting | Customer-Specific |  | Scheduling Hub - Generic Infra component | HRP | 1 | Low | High | XXL | 3.9 | 1.8333 | TBD |  | Defered
| RTB | Reporting | Tech-Upgrade |  | Infra components certification for cluster database in different zones (multi-subnet fail over property in connection string) | TECH | 4 | Low | Medium | XL | 2.6 | 4.9 | TBD |  | Yet to Start
| RTB | Reporting | Tech-Initiative |  | Provision to implement template-based report in ARI (dcube capability) | TECH | 1 | Low | High | XL | 2.6 | 2 | TBD |  | Defered
| RTB | Platform | Tech-Initiative | Glance | Glance Apis migration from V3 to V4 | TECH | 4 | Low | Medium | L | 1.95 | 5.3 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific |  | Approach and Changes for implementing Single DB approach | HRP | 1 | Medium | Medium | XL | 2.6 | 2.4 | TBD |  | Defered
| RTB | Reporting | Tech-Initiative | Reports Reuse | Approach for partner key /report id uniqueness | TECH | 4 | Medium | High | XXL | 3.9 | 5.3333 | TBD |  | Yet to Start
| RTB | InBox Montior | Tech-Initiative |  | Refactoring - Eliminating Quartz and Topshelf for workflow inbox monitor mdcf, workflow mailer | TECH | 4 | Medium | Medium | L | 1.95 | 5.8 | TBD |  | Yet to Start
| CTB | Reporting | Tech-Initiative |  | Reporting as Services : Role based access for Report Authorization | TECH | 2 | Medium | High | L | 1.95 | 4 | TBD |  | Yet to Start
| CTB | Reporting | Tech-Initiative |  | DCube Reports in UDS context ?? | TECH | 2 | Medium | Medium | XXL | 3.9 | 3.2667 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | POC - Reverse engineering platform modelled UIs to Glance | TECH | 4 | Low | High | XXL | 3.9 | 4.8333 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Provision to model dynamic tooltip for GQL based UI | TECH | 4 | Medium | Medium | M | 1.3 | 6.6 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | FITBIT enablement in all product model servers | TECH | 4 | Medium | Medium | M | 1.3 | 6.6 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Platform Modeling - Minimized Section and Sidebar | TECH | 4 | Medium | High | M | 1.3 | 7 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative | Glance | Glance Modeling - Minimized Section and Sidebar | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific |  | Using SMB or TCP protocol for report file access instead of UDB port 445 | HRP | 4 | Low | Medium | L | 1.95 | 5.3 | TBD |  | Defered
| RTB | MDCF | Tech-Initiative |  | Feasibility of eliminating Quartz in MDCF | TECH | 4 | Low | Medium | M | 1.3 | 6.1 | TBD |  | Yet to Start
| RTB | Workflow | Customer-Specific |  | Workflow Configuration - Success message in identified screens | ERP | 2 | Medium | Medium | M | 1.3 | 4.6 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific | Power BI | Approach for Managing License count for Power BI | PCO | 1 | Low | Medium | XXL | 3.9 | 1.7667 | TBD |  | Defered
| RTB | Platform | Customer-Specific | Glance | Glance modeling for Stepper Control | ERP | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Platform modeling for mouse hover popup section | ERP | 4 | Medium | High | M | 1.3 | 7 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific | Security | Vulnerability - Broken Access Control - Privilege Escalation Attack - Fixation for drill through reports | ERP | 4 | Medium | High | L | 1.95 | 6 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific | Power BI | Provision to launch power BI reports from application screen | PCO | 4 | Medium | High | XL | 2.6 | 5.5 | TBD |  | Defered
| RTB | Reporting | Customer-Specific | Power BI | Provision to pass different user & role name (currently context user and role) to power bi dataset | PCO | 4 | Medium | Medium | M | 1.3 | 6.6 | TBD |  | Defered
| RTB | Platform | Tech-Initiative | Glance | Glance Modeling - Auto Height for Grid Control | TECH | 4 | Low | Low | M | 1.3 | 5.5 | TBD |  | Yet to Start
| RTB | Reporting | Customer-Specific |  | Provision to export report schedule information in report metadata generation | LGT | 4 | Medium | High | M | 1.3 | 7 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Model Explorer - Migration to newer TECH Stack | TECH | 4 | Medium | High | L | 1.95 | 6 | TBD |  | Yet to Start
| RTB | Reporting | Tech-Initiative |  | Dcube migration tool - Migration to newer TECH Stack | TECH | 4 | Medium | Medium | XL | 2.6 | 5.4 | TBD |  | Yet to Start
| RTB | Audit Trial | Tech-Initiative |  | Audit trial - Migration to newer TECH Stack | TECH | 4 | Medium | Medium | XL | 2.6 | 5.4 | TBD |  | Yet to Start
| RTB | Workflow | Tech-Initiative |  | WF mail link code generator - Migration to newer TECH Stack | TECH | 4 | Medium | Medium | L | 1.95 | 5.8 | TBD |  | Yet to Start
| RTB | Platform | Dev-Productivity |  | In Refine service need to show the count of method mapped under that service before & after the update service (to avoid the mismatch of method count before and after the regeneration of services ) | HRP | 4 | Medium | Medium | XL | 2.6 | 5.4 | TBD |  | Yet to Start
| RTB | Workflow | Dev-Productivity |  | MDCF for workflow configurations | ERP | 4 | Medium | Medium | XXL | 3.9 | 5.2667 | TBD |  | Yet to Start
| RTB | Workflow | Dev-Productivity |  | MDCF for workflow rule configurator | HRP | 1 | Medium | Medium | XXL | 3.9 | 2.2667 | TBD |  | Yet to Start
| RTB | Workflow | Dev-Productivity |  | Org Structure based workflow approval | ERP | 1 | Medium | Medium | XL | 2.6 | 2.4 | TBD |  | Yet to Start
| RTB | Workflow | Dev-Productivity |  | Workflow engine SPs - Traceablity and troubleshooting logs in backend table | LGT | 4 | Low | Medium | XL | 2.6 | 4.9 | TBD |  | Yet to Start
| RTB | Platform | Tech-Initiative |  | Topic combo must be changed listedit in pub / sub event model screens | TECH | 1 | Low | Medium | M | 1.3 | 3.1 | TBD |  | Yet to Start
| RTB | MDCF | Tech-Initiative |  | Digital Signature for MDCF template generation (Macro enabled) | TECH | 4 | Medium | High | M | 1.3 | 7 | TBD |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Scripts to rollback component level ECR to any previous ECR | AVN | 4 | Medium | Very High | XXL | 3.9 | 5 | 2324-Q1 | 2023-06-01 | Yet to Start
| RTB | Workflow | Customer-Specific |  | Custom Parameters for Time based workflow | HRP | 1 | Medium | Medium | XL | 2.6 | 2.4 | TBD |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Need effective from and effective to columns in component - user - access control screen | ERP | 1 | Medium | High | M | 1.3 | 4 | TBD |  | Yet to Start
| RTB | Reporting | Tech-Upgrade |  | Reporting components - Build and test for .net framework 4.8 | TECH | 4 | Medium | Very High | XL | 2.6 | 5 | TBD |  | Yet to Start
| RTB | Workflow | Tech-Upgrade |  | Infra components - Build and test for .net framework 4.8 | TECH | 4 | Medium | Very High | XL | 2.6 | 5 | TBD |  | Yet to Start
| RTB | Platform | Tech-Upgrade |  | Platform Web RT - Build and test for .net framework 4.8 | TECH | 4 | Medium | Very High | XL | 2.6 | 5 | 2324-Q1 | 2023-06-01 | Yet to Start
| CTB | MDCF | Tech-Upgrade |  | MDCF as Services | TECH | 4 | Medium | Very High | XXL | 3.9 | 5 | TBD |  | Yet to Start
| CTB | Platform | Tech-Initiative |  | Platform Modernization - Hub activities with modern app layer infra(api / gql with caching) | TECH | 4 | High | Very High | XXL | 3.9 | 6 | TBD |  | Yet to Start
| RTB | Platform | Customer-Specific |  | Provision to specify Resource Histogram for Gantt Control | ERP | 1 | Medium | Medium | S | 0.65 | 5.2 | 2223-Q4 | 2023-03-01 | Yet to Start
| RTB | Reporting | Tech-Initiative |  | Analysis for excluding return url in report configuration | TECH | 4 | Medium | Very High | M | 1.3 | 5 | TBD |  | Defered
| RTB | Workflow | Dev-Productivity |  | HOD should approve a sp is written, since SP re-use is not there, they have to write sp for each use case | ERP | 1 | Medium | Medium | XXL | 3.9 | 2.2667 | TBD |  | Yet to Start
| RTB | MDCF | Tech-Initiative |  | Serilog / Additional Logger incorporation for service based MDCF | TECH | 4 | Medium | Medium | L | 1.95 | 5.8 | TBD |  | Yet to Start
| CTB | Reporting | Tech-Initiative |  | Reporting as Services - SSRS Reports - Import Mode | TECH | 2 | Medium | Medium | L | 1.95 | 3.8 | TBD |  | Defered
| CTB | Reporting | Dev-Productivity |  | Reporting as Services - SP Based ER Reports with pagination / scroll behaviour for high volume reports | TECH | 4 | Medium | Medium | XXL | 3.9 | 5.2667 | TBD |  | Yet to Start
| RTB | MDCF | Dev-Productivity |  | Duplicate caption handling in MDCF template generator and runtime | LGT | 2 | Low | Medium | XL | 2.6 | 2.9 | TBD |  | Yet to Start
| RTB | Workflow | Dev-Productivity |  | Provision to invoke custom parameter sp in application db (currently its expected and wfm40) | ERP | 1 | Medium | Low | XXL | 3.9 | 2.1667 | TBD |  | Yet to Start
| CTB | Platform | Tech-Initiative | Code Generators | Code Generation Integration with Devops (Provision to commit generated source code in git repo as part of code generation) | TECH | 4 | High | High | M | 1.3 | 8 | 2324-Q1 | 2023-05-01 | Yet to Start
| RTB | Reporting | Customer-Specific | Scheduler | Provide an option in Report scheduling screen to specify the Folder path under which the generated report is to be saved. All context parameters like OU, Username, Role, Service Name, Datetime should be available for the user to form the folder structure. Request the team to provide 2 level of nesting. For eg., first level folder can be Username and second level can be Datetime | ERP | [8 empty] | Yet to Start
| RTB | Reporting | Customer-Specific | Scheduler | Scheduler / Audit status screen to be enhanced to show the Link to the File generated | ERP | [8 empty] | Yet to Start
| RTB | Reporting | Customer-Specific | Scheduler | The screen should show audit for the links generated only by that user | ERP | [8 empty] | Yet to Start
| RTB | Reporting | Customer-Specific | Scheduler | For reports that can be scheduled should be based on the access privileges available to that user | ERP | [8 empty] | Yet to Start
| CTB | Workflow | Customer-Specific | Data Migration | Workflow - Provision to export / import data across environments with transformation | HRP | 1 | High | Very High | XXL | 3.9 | 3 | TBD |  | Yet to Start | # Should be a front end migration which functional consultant without any technical knowledge is able to complete # Should be able to migrate :Areacodewise , Pathwise ,OUwise . # Exported file can be imported to different server or withing same server wherein OU codes may vary from the source server. # There may be existing workflow for other OUs in the same server which should not be impacted with the new migration. # Overwriting of paths in destination server for OU where data is existing , can be allowed with a warning message and an acceptance from the project team. # Define Message also to be imported and yet again overwriting not allowed based on message id. # All the tabs which are part of rule configurator are to be migrated.
Note on A1: rTrack ID in tech backlog
Note on H1: "How many customers does this impact?"
Note on I1: "How does this contribute to our goal?" 3 for Very High, 2 for high, 1 for medium, 0.5 for low, 0.25 for very Low
Note on J1: "How confident you're that this delivers assigned Impact". 100% for high confidence, 80% for medium, 50% for low.
Note on K1: How hard will this be to implement 25 for S, 50 for M, 100 for L, 200 for XL, 300 for XXL.
Note on M1: Business value Time criticality Risk reduction Estimated size The WSJF score WSJF FAQ When SAFe, short for Scaled Agile Framework, was first introduced to help large organizations implement Agile and enable them to adapt to the changes faster it naturally came with its own prioritization method too. Weighted Shortest Job First (WSJF) prioritization model helps calculate and understand what is the level of the financial impact of not finishing the task of implementing the solution sooner than later. It's called Cost of Delay. This technique is built to speed up the delivery of value, especially in large projects where the big queues of issues can build up and waiting times are getting longer and longer. WSJF video explanation "If you prematurely invest all your time and money on the wrong idea, you have nothing left to try new ideas." - Alberto Savoia How to use WSJF method To calculate the Cost of Delay and WSJF score we need to first assign four metrics to our priorities - Business value, Time criticality, Risk reduction, and Estimated size. Business value When assessing Business value ask the question "How does this impact our business" and try to look at it from different angles. If you have your Goals or OKRs set you can see how much this task helps you to get closer to completing these. 1 for Lowest value 5 for Low value 8 for Medium value 13 for High value 20 for Highest value Business value metric in WSJF - How does this impact our business Business value in WSJF Time criticality Now it's time to asses "Is there a fixed deadline? Can we loose customers if it isn't completed in certain time?" Tasks with more tight and sooner deadlines have Higher Time criticality than ones with more loosen ones. 1 for Lowest 5 for Low 8 for Medium 13 for High 20 for Highest Time criticality in WSJF - Is there a fixed deadline? Time criticality in WSJF Risk reduction Risk reduction metric is great addition to the first one - Business value. Here we're asking "Is there any negative impact if we delay?" 1 for No risk 5 for Low risk 8 for Medium risk 13 for High risk 20 for Highest risk Risk reduction in WSJF - Is there any negative impact if we delay this task? Risk reduction in WSJF Estimated size Last question we ask is "How difficult is this to deliver" You can try to estimate how long it would take to deliver this task if one person would work on this in months. But you can also use T-shirt sizing to make it a bit easier. 1 for XS 5 for S 8 for M 13 for L 20 for XL Estimated size in WSJF - How difficult is this task to deliver? Estimated size in WSJF The WSJF score When we have all metrics assigned we can then calculate the cost of delay and the priority score. Cost of delay is a sum of business value, time criticality, and risk reduction. The Cost of delay helps quantify the impact of time on outcomes we’re hoping to achieve. To calculate the Weighted shortest job priority score divide Cost of delay with the Estimated size and you have it. The higher the WSJF priority score more important the task is.
Note on N1: Sam Jacob: 3 months forward: June, July, Aug (Firm Plan) 4 months there-after: Sep, Oct, Nov, Dec (Plan)
Note on P1: Sam Jacob: Planned, In-progress, Completed, Not Planned
Note on S1: Sam Jacob: Weekly progress notes, until the item is completed