## Technical
Tech id | Issues | clarification | Remarks
TECH-72400 | Process invoice Screen is not launching | Give a valid customclass name and write css in actvityilbo.css file and check..
TECH-72623 | Template is not shown | Problem is with the deployed template json. After correcting the same issue has been resolved.
TECH-72731 | Need clarification to use tooltip inside template icon | As discussed with Kalaivani,for handling of tooltip for icon inside the template kindly use the qtip property. Sample template json format has been shared to the user.
TECH-72773 | Unable to publish ECR | ECR got published after created synonyms in glossary. | fixed by tech team
TECH-72802 | Need clarification to use link inside template icon | As discussed kindly define expected taskinfo against the templteid in screen template json file and then check once.
TECH-72966 | Not able to find _HSeg Segment | 1. Segment loaded in the Model server. 2. For tooltip issue, after removing the ilbo association of the attribute dataitem "Hdn_Hdr_Mnscrn10" for the service "CSB_main_Srfet_CA", the issue got resolved. | Defect : if multiple services selected in Design service.
TECH-73235 | Need clarification to use dynamic icon in button
TECH-73236 | Not able to publish ECR | ECR got published after created newly updated hidden view synonym in glossary. | fixed by tech team
TECH-73247 | Extra controls are there during generate services |  | fixed by tech team
TECH-72932 | Getting error while launching manage invoice release - complex assembly screen |  | fixed by tech team
TECH-72903 | Getting error while ILBO mapping | Listview values passed as input after created separate method for listview controls.
TECH-72631 | while generating service , getting invalid error | As discussed already, Same hidden view bt synonym name is mapped for the two different controls under same page. This is due to the control movement across page. This is the wrong combination. For this, we will add validation in model. For retaining same parameter in Application SP, proceed with Manual service. If it needs to be Generate Service, change the hidden view bt synonym associated to the control in model. | Tech can validate
TECH-72596 | Getting Invalid error on publishing the ECR | For the service "CSB_main_Sr_Resou_CA",in the multi segment more than once different controls has been mapped.
TECH-72493 | Combo values not loading in the screen | As discussed kindly create columns for expected listview controls and then check once.
TECH-71306 | Codegen is getting failure | code gen completed , Kindly let know if any expected deliverable not available in share path.
TECH-71582 | Pub sub is not working . coming with wrong value | As discussed kindly unpublish and publish the latest ecr and do the codegen and deploy the latest deliverables and check Model data has been corrected | fixed by tech team
TECH-72907 | Activity dll is not getting generated for this two activity IINVAddIINV & IINVAddIINV_CA | open | To be fix by tech team
TECH-72769 | SP's is not firing on click of action apply and clear filter in resource tab of Mange Invoice Release - Complex Assembly | under the materials tab on click of apply button,"hdn_hdrmat_mat_view_cd" dataitem is provided with mandatory flag and value is not provided,
TECH-72907 | Activity dll not generated in codegen path | data problem corrected in dynamic tooltip | fixed by tech team

## Functional
Tech id | Issues | clarification | Remarks
TECH-73052 | Need new column- Column caption from Respective grid controls-In column grouping tab in addition with existing Column name/synonym. | open | New Requirement in RVW
TECH-72997 | Couple of columns which are visible in Grid columns but not visible in Preview/Column grouping | Kindly check with "grid control" group caption and revert for further clarifications. | Clarification
TECH-72825 | Need help in modelling Button Control as shown in wireframe | CSS code has been shared to the user to show the button as link. Kindly implement the given code in CSS file and check. | Clarification in modelling as per requirement
TECH-72784 | Unable to align the caption for control type-list view | Kindly change the data column width and label column width as per your requirement and check | To be fixed by tech(for listview align issue we need to fix in our code gen dll)
TECH-72776 | For scrap Info. columns are already mapped, but still on save- validation is thrown as no columns are mapped | Issue resolved by the user end after doing the proper column groupping. | Clarification given workaround
TECH-72775 | on click of save in column groupings tab, invalid validation is thrown | As discussed kindly provide data for both group name and group caption while creation. | Fixed by tech team
TECH-72720 | Pls change synonym of the control specified below | As per your request synonym names are update, Kindly check once and proceed. | validation needs to be handled by tech team
TECH-72564 | Primary violation key error is thrown on movement of controls from one section to other | Data problem. After correcting the data in the model, the issue got resolved. | Fixed by tech team
TECH-72525 | on click of publish wrq, invalid validation is thrown | As per user request, bt synonym name has been updated. | Fixed by tech team
TECH-72483 | Report link is outed as icon, but still it is outing with both caption and icon even when there is no property caption visible | Since link is a static control we need to provide --nocaption-- for the control so that caption does not appear in screen. | Clarification given for modelling
TECH-72482 | need help in modelling dynamic tab, in which vertical scroll bar should not come | Solutioning level changes has been explained to the user. 14-09-2022 Issue has been resolved after providing the tabsection height as 0 | Tech team suggested not possible in RVW. So resolved this issue with trial and error.
TECH-72453 | Need help in modelling vertical separator as shown in wireframe | Kindly check with UCD team for the vertical line. | Requested for modelling help but got template from UCD team