## Monthly Sprint
Sprint | Benefit | Theme | Work Item (User Story) | Unit | Function | Size | PSD | OPED | CPSD | CPED | Status | Primary | Estimate | rTrack ID | Unplanned | Requestor | Remarks
2021-08-01 | Adaptability | rTrack-Integration | rTrack Integration for ARI Reports | Rams-Infra | Reporting |  | 2021-08-11 |  |  |  | Hold |  | 15 | TECHB-534 |  | QLTY | Environment setup completed - use case narrowed - Open source HTML2Canvas not capturing content within iFrame. Details shared to Hub team
2021-08-21 | User Experience | KitchenSink | Grid Enhancement - Row Drag & Drop | Sampath |  |  | 2021-08-05 | 2021-08-18 | 2021-08-05 | 2021-08-18 | Deferred |  | 15 | TECHB-544 |  | TECH | Deprioritized - Will be taken later
2021-08-21 | Adaptability | Oracle | Oracle Iframe POC | Sampath |  |  | 2021-08-04 | 2021-08-18 | 2021-08-04 | 2021-08-18 | Completed |  | 10 |  |  | HCM - Bala | Feedback expected from RT/Oracle
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Rich Text HTML Editor (for message definition) | Rams-PlfRT | Workflow | High | 2021-09-17 | 2021-09-22 |  | 2021-10-31 | Completed |  | 10 | TECHB-581 |  | TECH
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Client Layer validations | Rams-PlfRT | Workflow | High | 2021-09-22 | 2021-09-22 |  | 2021-10-31 | Hold |  | 10 | TECHB-581 |  | TECH
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Server interaction components (API Manager) | Rams-PlfRT | Workflow |  | 2021-09-10 | 2021-09-22 |  | 2021-10-31 | Hold |  | 20 | TECHB-581 |  | TECH
2021-09-01 | Productivity | Workflow Designer | Middle layer code for exporting and importing diagram data to interface tables | Rams-Plf | Workflow | High | 2021-09-06 | 2021-09-30 |  | 2021-10-31 | Completed |  | 30 | TECHB-581 |  | TECH
2021-09-01 | Productivity | KitchenSink | Data View – Auto - Scroll, Page Scroll | Sampath |  |  | 2021-09-17 | 2021-09-21 | 2021-09-17 | 2021-09-21 | Completed |  | 3 | TECHB-587 |  | TECH
2021-09-01 | Productivity | KitchenSink | Data View – Default Template | Sampath |  |  | 2021-09-21 | 2021-09-27 | 2021-09-21 | 2021-09-27 | Completed |  | 5 | TECHB-588 |  | TECH
2021-09-01 | Productivity | Glance Hardening | BtSynonym – Lookup | Sampath |  |  | 2021-09-09 | 2021-09-22 | 2021-10-01 |  | Completed |  | 10 | TECHB-589 |  | TECH
2021-09-01 | Productivity | Grid Features | Export to PDF with Arabic language support | Sampath |  |  | 2021-09-06 | 2021-09-10 | 2021-10-01 |  | Wait |  | 5 | TECHB-590 |  | HCM
2021-09-01 | Productivity | UI-Improvement | Resolution based popup / callout window to be shown | Sampath |  |  | 2021-09-20 | 2021-09-23 | 2021-10-01 |  | Completed |  | 3 | TECHB-592 |  | HCM
2021-09-01 | Productivity | UI-Improvement | SOP Document for handconding within RVW (Sencha) | Sampath |  |  | 2021-09-13 | 2021-10-01 | 2021-10-01 | 2021-10-14 | Completed |  | 15 | TECHB-596 |  | TECH
2021-09-01 | Productivity | UI-Improvement | Client Side Validation - POC | Sampath |  |  | 2021-09-13 | 2021-10-01 | 2021-10-01 |  | Deferred |  | 15 | TECHB-596 |  | Nebula
2021-09-01 | Productivity | UI-Improvement | Client side local store - POC | Sampath |  |  | 2021-09-13 | 2021-10-01 | 2021-10-01 |  | Deferred |  | 15 | TECHB-596 |  | Nebula
2021-10-01 | Productivity | GQL | GQL Implementation POC | Sampath |  |  | 2021-10-01 | 2021-10-08 | 2021-10-01 | 2021-10-08 | Completed |  | 4 |  |  | TECH
2021-10-01 | Productivity | GQL | Platform Integration Sign Off | Sampath |  |  | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-10-11 | Completed |  | 2 |  |  | TECH
2021-10-01 | Productivity | GQL | Server Side Integration Sign Off | Sampath |  |  | 2021-10-11 | 2021-10-12 | 2021-10-11 | 2021-10-12 | Completed |  | 2 |  |  | TECH
2021-10-01 | Productivity | GQL | Client Access token (OIDC & RID V-4) | Sampath |  |  | 2021-10-07 | 2021-10-20 | 2021-10-07 | 2021-10-20 | Completed |  | 10 |  |  | TECH
2021-10-01 | Productivity | GQL | Client Runtime Using Apollo Client | Sampath |  |  | 2021-10-07 | 2021-10-20 | 2021-10-07 | 2021-11-12 | Completed |  | 10 |  |  | TECH
2021-10-01 | Productivity | GQL | Client Query / Mutation Calling | Sampath |  |  | 2021-10-14 | 2021-10-27 | 2021-10-14 | 2021-11-12 | Completed |  | 10 |  |  | TECH
2021-10-01 | Productivity | GQL | Client Grid Support Pagination | Sampath |  |  | 2021-10-21 | 2021-11-03 | 2021-10-21 | 2021-11-17 | Completed |  | 10 |  |  | TECH
2021-10-01 | Productivity | GQL | Client File Generation | Sampath |  |  | 2021-10-25 | 2021-11-05 | 2021-10-25 | 2021-11-19 | Completed |  | 10 |  |  | TECH
2021-10-01 | Productivity | UI-Improvement | Document Viewer - Third Party Library | Sampath |  |  | 2021-10-14 | 2021-10-18 | 2021-10-14 | 2021-10-18 | Completed |  | 2 |  |  | SRP
2021-10-01 | User Experience | Auto Rerouting | Workflow - Automatic rerouting based on document aging days | Rams-Infra | Workflow | Large | 2021-10-01 | 2021-11-01 |  |  | Completed |  | 60 | TECHB-621 |  | HRP
2021-10-01 | Productivity | ER | ER - Xml Report | Rams-Infra | Reporting |  | 2021-10-01 | 2021-11-01 |  |  | Cancelled |  | 45 | TECHB-571 |  | HRP
2021-10-01 | Cost | PowerBI | Managing License count for Power BI | Rams-Infra | Reporting | Medium | 2021-10-01 | 2021-11-01 |  |  | Completed |  | 30 | TECHB-622 |  | PROVISIONING
2021-10-01 | Productivity | SSRS | PDF Split using Python Library for SSRS Report | Rams-Infra | Reporting | Large | 2021-10-07 | 2021-10-15 |  |  | Completed |  | 15 | TECHB-630 |  | HRP
2021-10-01 | Cost | SSRS | Proxy service enablement to connect multiple SSRS URL | Rams-Infra | Reporting | Medium | 2021-10-04 | 2021-10-12 |  |  | Completed |  |  | TECHB-636 | Yes | HRP
2021-10-01 | User Experience | GSG | Fix for automatic STFP folder deletion in GSG_Interface Service | Rams-Infra | GSG | Medium | 2021-10-15 | 2021-10-21 |  |  | Completed |  |  | TECHB-633 | Yes | HRP
2021-10-01 | User Experience | GSG | File Decryption feature in IGSG | Rams-Infra | GSG | Medium | 2021-10-18 | 2021-10-27 |  |  | Completed |  |  | TECHB-634 | Yes | HRP
2021-10-01 | User Experience | GSG | Unknown/Special character issue in file upload | Rams-Infra | GSG | Small | 2021-10-21 | 2021-10-26 |  |  | Completed |  |  | TECHB-635 | Yes | HRP
2021-10-01 | Process | Release Mgmt | Improvements in release management for hot fix release | Rams-Plf | Platform | Medium | 2021-10-01 | 2021-10-19 |  |  | Completed |  | 20 | TECHB-618 |  | TECH
2021-10-01 | Process | Test Mgmt | Test Managements - Platform Scenarios for Setup Customer Project and Blue Print | Rams-Plf | Platform | High | 2021-10-01 | 2021-11-01 |  |  | Completed |  | 30 | TECHB-619 |  | TECH
2021-10-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Changes for HTML message editor, client layer validation, and system testing | Rams-PlfRT | Workflow | High | 2021-10-07 | 2021-11-01 |  |  | Completed |  | 35 | TECHB-626 |  | TECH
2021-10-01 | Security | Vulnerability | Workflow Notification - Connection String encryption in web.config | Rams-Infra | Workflow | Medium | 2021-10-01 | 2021-10-29 |  |  | Completed |  | 10 | TECHB-637 |  | AVN
2021-11-01 | Productivity | Workflow Designer | Visual Workflow Configurator - UCD Theme refactoring | Rams-PlfRT | Workflow |  | 2021-10-07 | 2021-11-01 |  | 2021-11-30 | Hold |  | 30 | TECHB-625 |  | TECH | (Approx. - 2 Weeks post UCD delivery)
2021-11-01 | User Experience | Reporting | POC for Reporting as Services - ER - SP Based Reports - Phase-1 | Rams-Infra | Reporting | Medium | 2021-09-01 | 2021-12-03 |  | 2021-12-03 | Completed |  | 40 | TECHB-580 |  | TECH
2021-11-01 | Productivity | Flexi Report | Flexi Report – Conditional Formatting | Rams-Infra | Reporting | Medium | 2021-10-01 | 2021-12-03 |  | 2021-12-03 | Completed |  | 45 | TECHB-611 |  | ERP
2021-11-01 | User Experience | Workflow Notification | Workflow - Selective email notification | Rams-Infra | Workflow | Large | 2021-11-08 | 2021-12-03 |  |  | Completed |  |  | TECHB-639 |  | HRP
2021-11-01 | Productivity | Workflow Notification | Workflow reminder notification to approvers after x days of delay | Rams-Infra | Workflow |  | 2021-11-08 | 2021-12-03 |  |  | Clarified |  |  | TECHB-640 |  | HRP
2021-11-01 | Tech Upgrade | MSDTC Removal | Time-based Workflow - MSDTC removal changes in custom BRO | Rams-Infra | Workflow | Large | 2021-11-08 | 2021-12-03 |  |  | Completed |  |  | TECHB-641 |  | HRP
2021-11-01 | Tech Upgrade | Workflow Inbox Monitor | POC for MSGraph Api based Inbox Monitor | Rams-Infra | InBox Montior | High | 2021-11-08 | 2021-12-03 |  |  | Completed |  |  | TECHB-642 |  | HRP | Initial POC completed - From Velayutham R backup an existing code base identified and validated. This repo will tested and moved to development / production
2021-11-01 | Tech Upgrade | Session Out of Proc | Plf Web RT changes for Session out of Proc | Rams-Plf | Platform | High | 2021-11-10 | 2021-12-03 |  |  | Completed |  |  | TECHB-651 |  | TECH
2021-11-01 | Tech Upgrade | Packaging | Release Manager Changes For Product Group and Multi Version | Rams-Plf | Platform | High | 2021-11-17 | 2021-12-03 |  |  | Completed |  |  | TECHB-656 | Yes | TECH
2021-11-01 | Process | Test Mgmt | Test Managements - Platform Scenarios for Download Work Request, Specify Layout (Basic Controls) and Publish Work Request | Rams-Plf | Platform | High | 2021-11-01 | 2021-12-03 |  |  | Completed |  |  | TECHB-662 |  | TECH
2021-12-01 | Productivity | GQL | Activity DLL Generator changes for GQL | Rams-Plf | Platform | Medium | 2021-12-06 | 2021-12-17 |  |  | Completed |  |  | TECHB-658 |  | TECH
2021-12-01 | Productivity | GQL | Integrating GQL client side generator with main stream code generator | Rams-Plf | Platform | Medium | 2021-12-06 | 2021-12-17 |  |  | Completed |  |  | TECHB-660 |  | TECH
2021-12-01 | Productivity | GQL | Code Generation JSON for GQL Query - Control mapping | Rams-Plf | Platform | High | 2021-12-06 | 2021-12-10 |  |  | Completed |  |  | TECHB-663 |  | TECH
2021-12-01 | Productivity | GQL | System testing UI development for GQL Phase-1 Release | Rams-Plf | Platform | High | 2021-12-06 | 2021-12-31 |  |  | Completed |  |  | TECHB-659 |  | TECH
2021-12-01 | User Experience | UI-Improvement | Provision to map associated control for Multi Select List | Rams-Plf | Platform | Medium | 2021-12-06 | 2021-12-31 |  |  | Completed |  |  | TECHB-657 |  | SRP
2021-12-01 | Productivity | UI-Layouting | Provision to manage smart search control mapping via Handle Changes DB | Rams-Plf | Platform | Medium | 2021-12-06 | 2021-12-31 |  |  | Completed |  |  | TECHB-653 |  | AVN
2021-12-01 | Tech Upgrade | Session Out of Proc | Reporting & Infra changes for Session out of Proc | Rams-Infra | Reporting | Large | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-694 |  | TECH
2021-12-01 | User Experience | Reporting | Critical Defect - Overwrite same schedule created with different user logins | Rams-Infra | Reporting | Small | 2021-12-01 | 2021-12-31 |  |  | Completed |  |  | TECHB-664 |  | SRP
2022-01-01 | Tech Upgrade | Packaging | Infra Packaging - 1.2.4.0 | Rams-Infra | Reporting | Large | 2022-01-01 | 2022-01-31 |  |  | Completed |  |  | TECHB-698 | Yes | HRP
2022-01-01 | Tech Upgrade | Packaging | Decision Works Packaging - 1.1.40.0 | Rams-Infra | Workflow | Large | 2022-01-01 | 2022-01-31 |  |  | Completed |  |  | TECHB-699 |  | HRP
2022-01-01 | Security | Vulnerability | Vulnerability fixation for 1. Disabling Forced Browsing 2.Preventing XSS Cross site scripting 3.Sensitive Information Disclosure | Rams-Infra | Reporting | Large | 2022-01-01 | 2022-01-31 |  |  | Completed |  |  | TECHB-700 | Yes | HRP | SCOGEN
2022-01-01 | Productivity | GQL | Platform - GQL - Modeling Capabilities - Phase-I | Rams-Plf | Platform | High | 2021-10-01 | 2021-11-01 |  |  | Completed |  | 60 | TECHB-617 |  | TECH
2022-01-01 | Productivity | GQL | Platform - Capability to import GQL introspection into platform model | Rams-Plf | Platform | High | 2021-10-01 | 2021-11-01 |  |  | Completed |  | 30 | TECHB-617 |  | TECH
2022-01-01 | Productivity | GQL | Platform - Code gen feed for gql code generator (DB Record set based) | Rams-Plf | Platform | High | 2021-10-01 | 2021-11-01 |  |  | Completed |  | 30 | TECHB-624 |  | TECH
TBD | User Experience | GQL | Provision to launch gql app studio from design engineering with context, customer, project and ECR number | Rams-Plf | Platform | [5 empty] | Completed |  | 10 | TECHB-638 | Yes | TECH
2022-01-01 | User Experience | Reporting | RawData Text Report - New report type addition | Rams-Infra | Reporting | Large | 2022-01-01 | 2022-01-31 |  |  | Completed |  |  | TECHB-701 |  | HRP | Sunway
2022-01-01 | Productivity | Reporting | Concentrix - RawData excel - Alternate for approach for high volume ARI report (salary register) | Rams-Infra | Reporting | [5 empty] | Clarified |  |  |  |  | HRP | Concentrix - feature already available - requested support team to take it forward
2022-01-01 | Security | Vulnerability | Log4j 2.17.1 library upgrade | Rams-Infra | Reporting | Large | 2022-01-01 | 2022-01-31 |  |  | Completed |  |  | TECHB-702 | Yes | HRP | QMG
2022-01-21 | Productivity | Vulnerability | SessionId should not be in part Response | Sampath |  |  | 2022-01-01 | 2022-01-31 | 2022-01-01 | 2022-01-31 | Completed
2022-01-21 | Productivity | UI-Improvement | Google Maps with Multi Root | Sampath |  |  | 2022-01-01 | 2022-01-31 | 2022-01-01 | 2022-01-31 | Completed
2022-01-21 | Productivity | UI-Improvement | Performance improvement on initial page loading | Sampath |  |  | 2022-01-01 | 2022-01-31 | 2022-01-01 | 2022-01-31 | Completed |  |  | TECHB-686
2022-01-21 | Productivity | Vulnerability | CKEditor - 4.17.1 | Sampath |  |  | 2022-01-01 | 2022-01-31 | 2022-01-01 | 2022-01-31 | Completed
2022-01-21 | Productivity | Localization | Portuguese Language Translator | Sampath |  |  | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | Completed
2022-01-21 | Productivity | GQL | Client Call GQL - Phase-1 | Sampath |  |  | 2022-01-01 | 2022-01-31 | 2022-01-01 | 2022-01-31 | Completed |  |  | TECHB-684
2022-02-01 | Productivity | Workflow | Changes for enabling custom parameter and pass customer parameter values as individual or consolidated value | Rams-Infra | Workflow | Large | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-691 |  | HRP
2022-02-01 | Tech Upgrade | Azure SQL MI | Verification of Infra components for Azure SQL Managed Instance | Rams-Infra | Reporting | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-690 |  | HRP | Policy Bazar
2022-02-01 | Security | Vulnerability | Enabling code generator option for Attach document server side fileid changes | Rams-Plf | Platform | High | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-681 |  | HRP | SCOGEN
2022-02-01 | Security | Vulnerability | Activity DLL Generator changes for Attach document server side fileid changes | Rams-Plf | Platform | High | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-680 |  | HRP | SCOGEN
2022-02-01 | Usability | Localization | Multi language support for Workflow My Page Administrator components - French and Portuguese | Rams-Infra | Workflow | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-669 |  | HRP | French and Portuguese
2022-02-01 | User Experience | Reporting | ARI Report Export - To be downloaded in same window - Disabling download in new blank window | Rams-Infra | Reporting | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-670 |  | HRP | OOH Media
2022-02-01 | User Experience | Reporting | Reporting engine - Heap memory alert notification | Rams-Infra | Reporting | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-672 |  | CIS
2022-02-01 | Audit | Audit Reports | DW classic version - Authentication and Application Activity Access & Action Audit Log - GET Apis (SP based report) | Rams-Infra | Reporting | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-673 |  | AVN | Emirates
2022-02-01 | Productivity | InBox Monitor | Tenant level NT Service for POP3 & IMAP Inbox monitor | Rams-Infra | InBox Montior | Extra Large | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-674 |  | HRP
2022-02-01 | Productivity | Change Log | Platform change log reports for accessing test complete script impact | Rams-Plf | Platform | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-692 |  | ERP
2022-08-01 | Productivity | Model | Aviation model migration and rollout .NET based code generator | Rams-Plf | Platform | High | 2022-08-01 | 2022-08-31 |  |  | Completed |  |  | TECHB-703 |  | AVN
2022-02-01 | Productivity | Template Designer | Web based Template designer in platform | Rams-PlfRT | Platform |  | 2022-01-01 | 2022-02-28 |  |  | Hold |  |  | TECHB-676 |  | TECH
2022-02-01 | Productivity | Inbox Monitor | Implementation Support for MSGraph Api based InBox Monitor | Rams-Infra | InBox Montior | Extra Large | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-693 |  | HRP | Dabur
2022-02-01 | Productivity | Change Log | Provision to track history of changes related to control type and task pattern | Rams-Plf | Platform | Medium | 2022-02-01 | 2022-02-28 |  |  | Completed |  |  | TECHB-753 | Yes | ERP
2022-02-21 | Productivity | GQL | Client Call GQL - Phase 2 | Sampath |  |  | 2022-02-01 | TBD |  |  | In Progress |  |  | TECHB-685 |  | TECH
2022-02-21 | Productivity | UI-Improvement | Google Map - Features | Sampath |  |  | 2022-02-14 | 2022-02-28 | 2022-02-14 | 2022-02-28 | Completed |  |  | TECHB-688 |  | LGT
2022-02-21 | Productivity | UI-Improvement | Bryntum Gantt - Features POC | Sampath |  |  | 2022-02-14 | 2022-02-28 | 2022-02-14 | 2022-03-04 | Completed |  |  | TECHB-687 |  | ERP
2022-02-21 | Productivity | UI-Improvement | Extjs7.5.0 - Upgrade | Sampath |  |  | 2022-02-14 | 2022-03-31 | 2022-04-01 | 2022-04-15 | Hold |  |  | TECHB-689 |  | TECH
2022-02-21 | Productivity | Vulnerability | Client JSON code generator option for Attach document | Sampath |  |  | 2022-02-14 | 2022-02-28 | 2022-02-14 | 2022-02-28 | Completed |  |  | TECHB-696 |  | HRP | SCOGEN
2022-02-21 | Productivity | Vulnerability | Client Runtime option for Attach document | Sampath |  |  | 2022-02-14 | 2022-02-28 | 2022-02-14 | 2022-02-28 | Completed |  |  | TECHB-697 |  | HRP | SCOGEN
2022-03-01 | User Experience | Workflow Rejection | Workflow - POC and Concept for State level rejection | Rams-Infra | Workflow | Extra Large | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-618 |  | SRP
2022-03-01 | Tech Upgrade | Security | POC for eMudhra client side signing with multiple signatures (dongle based) | Rams-Infra | Reporting | Extra Large | 2022-02-01 | 2022-02-28 |  | 2022-03-31 | Completed |  |  | TECHB-682 |  | ERP | Super Sales
2022-03-01 | User Experience | Reporting | Number to Words convertor for 3 decimal place | Rams-Infra | Reporting | Medium | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-779 |  | ERP
2022-03-01 | User Experience | Delegation | Delegation - Validation for activity authorization | Rams-Infra | Workflow | Small | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-786 |  | HRP
2022-03-01 | Productivity | UI-Improvement | Pre/Post Task for file Attachment | Sampath |  |  | 2022-03-14 | 2022-02-21 | 2022-03-14 | 2022-02-21 | Completed |  |  | TECH-66629 |  | AVN
2022-03-01 | Productivity | UI-Improvement | Launching a Popup UI or Popup screen on click of Multi File upload(Any of the File) in the context of file name) | Sampath |  |  | 2022-03-14 | TBD | [5 empty] | TECH-66628 |  | AVN
2022-03-01 | Productivity | UI-Improvement | Conditional based Applying user formats for numeric values | Sampath |  |  | 2022-03-01 | 2022-03-04 | 2022-03-01 | 2022-03-04 | Completed |  |  |  |  | HRP | Tata eleix
2022-03-01 | Productivity | UI-Improvement | Mandatory marking for multiline using Chrysalis | Sampath |  |  | 2022-03-22 | 2022-03-31 |  |  | Completed |  |  | TECH-62114 |  | HRP | Tata eleix
2022-03-01 | Productivity | UI-Improvement | Bryntum Gantt - Features filter - code generator | Sampath |  |  | 2022-03-22 | TBD |  |  | In Progress |  |  | TECHB-687 |  | ERP
2022-03-01 | User Experience | GQL | Follow-up Task - Platform Modeling Screen changes for GQL mapping | Rams-Plf | Platform | Medium | 2022-03-14 | 2022-03-31 |  |  | Completed |  |  | TECHB-746 |  | TECH
2022-03-01 | User Experience | GQL | Provision to specify PSR, PMR, PSMR for array arguments and input fields | Rams-Plf | Platform | Medium | 2022-03-07 | 2022-03-31 |  |  | Completed |  |  | TECHB-747 |  | TECH
2022-03-01 | User Experience | Design | Follow-up Task - Provision to suppress success message | Rams-Plf | Platform | Medium | 2022-03-14 | 2022-03-31 |  |  | Completed |  |  | TECHB-750 |  | AVN
2022-03-01 | Productivity | GQL | Platform - Code gen feed for gql phase-2 (hidden views, post task, disposal task, follow-up task) | Rams-Plf | Platform | High | 2022-03-07 | 2022-03-31 |  |  | Completed |  |  | TECHB-751 |  | TECH
2022-03-01 | Usability | Localization | Multi language support for Dcube - French and Portuguese | Rams-Infra | DCube | Medium | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-780 |  | HRP
2022-03-01 | Tech Upgrade | Code Generator | Java service code generator changes for log4j implementation | Rams-Plf | Platform | Medium | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-756 |  | TECH
2022-03-01 | User Experience | UI-Improvement | Provision to specify nodelines style for tree and tree grid - Platform | Rams-Plf | Platform | Low | 2022-03-20 | 2022-03-31 |  |  | Completed |  |  | TECHB-755 |  | AVN
2022-03-01 | Tech Upgrade | Reporting | Python latest version upgrade (pdf encryption) | Rams-Infra | Reporting | Medium | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-781 |  | HRP
2022-03-01 | Productivity | MDCF | Compensatory for auto restart of mdcf services (current version-3.7.4 latest version-3.10.3) | Rams-Infra | MDCF | Medium | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-797 |  | AVN
2022-03-01 | User Experience | Advanced Reports | Flexi Report – Null handling for measure values | Rams-Infra | Reporting | Small | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-787 |  | ERP
2022-03-01 | Tech Upgrade | Security | Encryption of sa password in DW logs | Rams-Infra | Reporting | Small | 2022-03-01 | 2022-03-31 |  |  | Completed |  |  | TECHB-788 |  | ERP
2022-03-01 | Productivity | UI-Improvement | Grouping Column Locking Feature | Sampath |  |  | 2022-03-14 | 2022-03-31 |  |  | Completed |  |  | TECH-65899 |  | AVN
2022-04-01 | User Experience | Design | Provision to specify PSR, PMR, PSMR in design service and design refinements | Rams-Plf | Platform | Medium | 2022-03-07 | 2022-04-30 |  |  | Completed |  |  | TECHB-749 |  | ERP
2022-04-01 | Productivity | UI-Improvement | Platform Modeling - Post and Pre Task for Attachment controls | Rams-Plf | Platform | Medium | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-776 |  | AVN
2022-04-01 | User Experience | Inbox | InBox Refinements - HRP requirements | Rams-Infra | InBox | Medium | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-795 |  | HRP
2022-04-01 | Productivity | UI-Improvement | Platform Modeling - System populate hidden controls for filtering capabilities in Gantt, Scheduler and Calendar | Rams-Plf | Platform | Medium | 2022-04-05 | 2022-04-22 |  |  | Completed |  |  | TECHB-777 |  | ERP
2022-04-01 | Productivity | UI-Improvement | GQL - Provision to model dynamic caption for control, column, section and page | Rams-Plf | Platform | Medium | 2022-04-15 | 2022-04-30 | Completed |  | Completed |  |  | TECHB-896 |  | TECH
2022-04-01 | User Experience | Controls | Platform modeling for bulk file download as zip file | Rams-Plf | Platform | Medium | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-778 |  | AVN
2022-04-01 | Tech Upgrade | Reporting | “Myanmar3” - New font addition for Burmese literals in report designer | Rams-Infra | Reporting | Small | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-783 |  | HRP
2022-04-22 | Productivity | UI-Improvement | Combo control without borders | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-758 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Edit control with actionable more information icon | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-759 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Vertical column separators / Layout style properties across columns in a section | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-760 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Displayonly column with actionable more information action (with prefix and suffix options) | Sampath |  | Small | 2022-05-16 | 2022-05-27 |  |  | Yet To Start |  |  | TECHB-761 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Add Action for Edit Control | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-763 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Display Control with Border and background color (button style) | Sampath |  | Small | TBD | [6 empty] | TECHB-764 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Common caption for 2 adjacent controls | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-765 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Section title to have Icon Prefix | Sampath |  | Small | TBD | [6 empty] | TECHB-766 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Provision to design section border styles - Position, Style and Color | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-767 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Dynamic color in display only control in supplier details side drawer screen | Sampath |  | Small | TBD | [6 empty] | TECHB-768 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Switch control | Sampath |  | Small | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-769 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Actions & links in Panel title section | Sampath |  | Small | 2022-05-16 | 2022-05-27 |  |  | Yet To Start |  |  | TECHB-770 |  | ERP
2022-04-22 | Productivity | UI-Improvement | Bubble error | Sampath |  | Large | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-771 |  | RT
2022-04-22 | Productivity | UI-Improvement | Download Selected Downloadable file as zip | Sampath |  | Medium | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-772 |  | AVN
2022-04-01 | Productivity | UI-Improvement | HRP Inbox requirements | Sampath |  | Medium | 2022-04-18 | 2022-04-29 |  |  | Completed |  |  | TECHB-773 |  | HRP
2022-04-01 | User Experience | Workflow | Workflow Configuration - Multiple roles for notifications messages and provision to specify CC roles with contextual inputs | Rams-Infra | Workflow | Large |  |  |  |  | Completed |  |  | TECHB-784 |  | HRP
2022-04-01 | Tech Upgrade | GSG | Excel reader - Implementing Document.Openxml instead of OLEDB (Issue with VLOOKUP and cell level warnings) | Rams-Infra | GSG | Medium | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-789 |  | HRP
2022-04-01 | Productivity | GSG | Exception handling and logger enhancements in file processing module - Provision to ignore erroneous documents and continue processing other documents | Rams-Infra | GSG | Small | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-790 |  | HRP
2022-04-01 | Productivity | GSG | Performance optimization for inserting bulk data through GSG_MDCF Service | Rams-Infra | GSG | Medium | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-791 | Yes | HRP
2022-04-01 | Productivity | GSG | Provision to backup MDCF data files in a SFTP path | Rams-Infra | GSG | Medium | 2022-04-01 | 2022-04-30 |  |  | Completed |  |  | TECHB-792 | Yes | HRP
2022-05-01 | Productivity | GQL | GQL - Phase-2A development of test screen (Sale Order hub) | Rams-Plf | Platform | High | 2022-03-07 | 2022-05-31 |  |  | Completed |  |  | TECHB-752 |  | TECH
2022-05-01 | Tech Upgrade | Developer Experience | POC for embedding graphql voyager (visually representing GraphQL schema) in manage task | Rams-Plf | Platform | High | 2022-04-01 | 2022-05-31 |  |  | Completed |  |  | TECHB-754 |  | TECH
2022-05-01 | User Experience | Errors | Modeling and Code Generator changes for Bubble error messages | Rams-Plf | Platform | High | 2022-04-01 | 2022-05-31 |  |  | Completed |  |  | TECHB-233 |  | ERP
2022-05-01 | User Experience | UI-Controls | Platform modeling for Custom Borders, Multiple actions for header controls and Switch Control | Rams-Plf | Platform | Medium | 2022-05-16 | 2022-06-15 |  |  | Completed |  |  | TECHB-805 |  | ERP
2022-05-01 | Tech Upgrade | Security | Reports Designer and ARI Reports - Upgrading JQuery libraries from version 1.2 to 3.6 | Rams-Infra | Reporting | Large | 2022-05-01 | 2022-05-31 |  |  | Completed |  |  | TECHB-800 |  | TECH
TBD | Usability | Localization | Dcube - Multilanguage - Schema Changes | Rams-Infra | DCube | [5 empty] | Yet To Start |  |  | TECHB-801 |  | HRP
2022-05-01 | User Experience | UI-Improvement | Scheduled Report - Applying user preference for both SP and Service based scheduled reports | Rams-Infra | Reporting | Medium | 2022-05-01 | 2022-05-31 |  |  | Completed |  |  | TECHB-802 |  | AVN
2022-05-01 | Productivity | Workflow | Custom Parameters for Time based workflow | Rams-Infra | Workflow |  | 2022-05-01 |  |  |  | Hold |  |  |  |  | HRP | More inputs awaited from HRP team
2022-05-01 | Usability | Localization | Dcube - UI Literals and error translation for Korean language | Rams-Infra | DCube | Medium | 2022-05-10 | 2022-06-15 |  |  | Completed |  |  | TECHB-803 |  | HRP | Syngenta
2022-05-01 | Tech Upgrade | Security | Reporting - Enabling TLS1.2 to send email. | Rams-Infra | Reporting | Small | 2022-05-15 | 2022-05-31 |  |  | Completed |  |  | TECHB-807 | Yes | HRP
2022-05-01 | Usability | Reporting | Jasper report to support more than 5 digits precision value. | Rams-Infra | Reporting | Medium | 2022-05-10 | 2022-05-31 |  |  | Completed |  |  | TECHB-808 | Yes | ERP | EBS
2022-05-01 | Workflow | Workflow Role | Workflow Role addition in user identification screen for enable notification messages | Rams-Infra | Workflow | Medium | 2022-05-26 | 2022-06-15 |  |  | Completed |  |  | TECHB-809 |  | HRP
2022-05-01 | User Experience | Inbox | Inbox Refinements - Area, Advanced Filters and Grouping - Consolidation of multiple workflow documents to a single inbox document (grouping based on CATKEY metadata) | Rams-PlfRT | InBox | High | 2022-05-10 | 2022-06-15 |  |  | Completed |  |  | TECHB-804 |  | HRP
2022-05-01 | User Experience | UI-Controls | HERE Maps version upgrade Runtime version from 3.1.18.1 to 3.1.30.15, Routing Apis from V7.1 to V8 | Rams-PlfRT | Platform | High | 2022-05-20 | 2022-06-08 |  |  | Completed |  |  | TECHB-806 | Yes | LGT
2022-05-01 | User Experience | UI-Controls | Glance modeling for Custom Borders, Multiple actions for header controls, Switch and Line Control | Rams-PlfRT | Platform | Medium | 2022-05-16 | 2022-06-15 |  |  | Completed |  |  | TECHB-810 |  | ERP
2022-05-01 | Productivity | UI-Improvement | Dynamic row height in Tree grid control | Sampath |  | Small | 2022-05-02 | 2022-05-13 |  |  | Completed |  |  | TECHB-811 |  | AVN
2022-05-01 | Productivity | UI-Improvement | Download file inside template control | Sampath |  | Small | 2022-05-02 | 2022-05-13 |  |  | Completed |  |  | TECHB-812 |  | AVN
2022-05-01 | Productivity | UI-Improvement | Section with one row - On expand it should show all rows in that section | Sampath |  | Small | 2022-05-16 | 2022-05-27 |  |  | Completed |  |  | TECHB-762 |  | ERP
2022-05-01 | Productivity | UI-Improvement | Bottom Static Section | Sampath |  | Small | 2022-05-16 | 2022-05-27 |  |  | Completed |  |  | TECHB-813 |  | ERP
2022-05-01 | Productivity | UI-Improvement | Collapsible right pane with minimize, maximize and toggle views | Sampath |  | Small | TBD | [6 empty] | TECHB-815 |  | ERP
2022-05-01 | Productivity | UI-Improvement | Bubble error Enhancement | Sampath |  | Large | 2022-05-23 |  |  |  | Completed |  |  | TECHB-771 |  | RT
2022-05-01 | Productivity | UI-Improvement | Hidding/Disable Export button in ML Grid | Sampath |  | Small | 2022-05-16 | 2022-05-27 |  |  | Completed |  |  | TECHB-816 |  | AVN
2022-05-01 | Productivity | UI-Improvement | HRP Inbox requirements- Enhancement | Sampath |  | Large | 2022-05-16 | 2022-05-27 |  |  | Completed |  |  | TECHB-773 |  | HRP
2022-05-01 | Productivity | Security | Leaflet version upgrade from 1.3.4 to 1.8 | Sampath |  | Medium | 2021-06-01 | 2022-06-30 | [5 empty] | TECHB-817 |  | Tech
2022-06-01 | Productivity | GQL | POC - GraphQL - Reporting System Queries - ER SP Based Report | Rams-Infra | Platform | Medium | 2022-05-01 | 2022-06-30 |  |  | Completed | Niranjan P |  | TECHB-794 |  | TECH
2022-06-01 | Productivity | MDCF | POC for .Net Core based Inbox monitor (Linux) | Rams-Infra | InBox Montior | Large | 2022-06-01 |  |  |  | Hold | Vigneshwari S |  |  |  | AVN | ERA
2022-06-01 | Tech Upgrade | Scheduler | Quartz.net version upgrade from 3.0.7 to 3.4.0 (critical defect fixes w.r.t to ideal state) for MDCF | Rams-Infra | MDCF | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed | Akila R |  | TECHB-820 |  | TECH
2022-06-01 | User Experience | Advanced Reports | ARI Reports - Data Export to PDF for dynamic report columns | Rams-Infra | Reporting | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed | Niranjan P |  | TECHB-821 |  | ERP
2022-06-01 | Security | Audit Logs | DW classic version - Apis for Application Authentication and Activity Access audit logs | Rams-Infra | Reporting | Medium | 2022-05-26 | 2022-06-24 |  |  | Completed | Muthulakshmi |  | TECHB-822 |  | AVN | Emirates
2022-06-01 | Security | License | Approach for removal of winword in web server for Dcube template based word and pdf reports | Rams-Infra | DCube | Large | 2022-05-26 | 2022-07-15 |  |  | Completed |  |  | TECHB-823 |  | SRP / Provisioning / IMG | Adecco
2022-06-01 | User Experience | ER Reports | Provision to download ER Sp-based report files in user defined file naming convention / format (current format - ER: {userid_reportid_guid}, ARI - {userid_reportid_datetime}) | Rams-Infra | Reporting | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed | Akila R |  | TECHB-824 |  | BPO | GE
2022-06-01 | Tech Upgrade | GraphQL | Approach for workflow enablement in GraphQL Context | Rams-Infra | Workflow | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed |  |  | TECHB-825 |  | TECH
2022-06-01 | Tech Upgrade | Services | Topshelf version upgrade from 4.2.1 to 4.3.0 for MDCF | Rams-Infra | MDCF | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed | Akila R |  | TECHB-826 |  | TECH
2022-06-01 | Tech Upgrade | Workflow | Provision to stop workflow mailers for completed documents when services restarted | Rams-Infra | Workflow | Large | 2022-06-01 | 2022-06-30 |  |  | Completed | Raja Priyaa |  | TECHB-827 |  | TECH
2022-06-01 | User Experience | UI-Controls | Platform modeling - Changes for Responsive Layout | Rams-Plf | Platform | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed |  |  | TECHB-828 |  | TECH
2022-06-01 | User Experience | UI-Controls | Platform modeling for Section and Page level toolbar | Rams-Plf | Platform | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed |  |  | TECHB-831 |  | ERP
2022-07-01 | Productivity | GQL | GQL - System testing for GQL Phase-2A & 2B Features (Sale Order hub) | Rams-Plf | Platform | High | 2022-06-01 | 2022-06-30 |  |  | Completed | Venkatesh |  | TECHB-832 |  | TECH
2022-06-01 | Training | Platform | Unify mobile modeling training Session for ERP team | Rams-Plf | Platform | Medium | 2022-06-01 | 2022-06-15 |  |  | Completed |  |  | TECHB-833 |  | ERP
2022-06-01 | User Experience | Process Support | Hot fix release repo movement from file server to git | Rams-Plf | Platform | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed |  |  | TECHB-829 |  | TECH
2022-06-01 | User Experience | UI-Controls | Platform modeling for Section tools | Rams-Plf | Platform | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed |  |  | TECHB-830 |  | ERP
2022-06-01 | User Experience | UI-Controls | Glance modeling for Section tools | Rams-PlfRT | Platform | Medium | 2022-05-16 | 2022-07-31 |  |  | Hold | Giri |  | TECHB-834 |  | ERP
2022-06-01 | User Experience | UI-Controls | Glance modeling for Section and Page level toolbar | Rams-PlfRT | Platform | Medium | 2022-05-16 | 2022-07-31 |  |  | Hold | Giri |  | TECHB-837 |  | ERP
2022-06-01 | Productivity | UI-Improvement | Request to Provide provision to modify the Radius boundary details in Map View | Sampath |  | Medium | 2021-06-01 | 2022-06-10 |  |  | Completed |  |  | TECHB-818 |  | AVN
2022-06-01 | Productivity | UI-Improvement | Request to provision to Displaying radius as boundary in Map | Sampath |  | Medium | 2021-06-01 | 2022-06-10 |  |  | Completed |  |  | TECHB-819 |  | AVN
2022-06-01 | Productivity | UI-Improvement | Option to show Resource Histogram at Brytum Gantt Chart | Sampath |  | Large | 2021-06-01 | 2022-06-10 |  |  | Completed |  |  | TECHB-687 |  | ERP
2022-06-01 | Productivity | GQL | Template Concept (Client or Server) | Sampath |  | Medium | 2021-06-01 | 2022-06-15 | [7 empty] | TECH
TBD | Productivity | UI-Improvement | Dynamic visible Rows with pesist | Sampath |  | Small | [9 empty] | TECH
TBD | Tech Upgrade | Services | Topshelf version upgrade from 4.2.1 to 4.3.0 for InBox Monitor | Rams-Infra | InBox Montior | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | User Experience | Inbox | New InBox - Phase 1 Changes | Rams-Infra | InBox | [5 empty] | Yet To Start |  |  | TECHB-644 |  | TECH
TBD | Security | Vulnerability | CSP Changes for Reporting Components - Phase-1 | Rams-Infra | Reporting | [5 empty] | Yet To Start |  |  | TECHB-643 |  | TECH
2022-07-01 | Adaptability | Workflow Purging | Workflow Inbox message - Alternative approach for high volume data purge | Rams-Infra | Workflow | Large | 2022-07-01 | 2022-07-31 |  |  | In Progress | Raja Priyaa |  | TECHB-895 |  | TECH | Concentrix
TBD | User Experience | Workflow | Provision to invoke custom parameter sp in application db (currently its expected and wfm40) | Rams-Infra | Workflow | [5 empty] | Yet To Start |  |  |  |  | TECH
TBDQ | Productivity | Mailer | Need to configure multiple From Mail Id option for Workflow / Nextgen workflow / Schedule reports for RCT Project | Rams-Infra | Workflow | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | Productivity | Design | Provision to generate filling methods for listedit, combo, charts without FlowBR | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | User Experience | Design | Provision to specify task pattern in design engineering | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Productivity | UI-Improvement | Glance - Quick / Combo Link | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Productivity | UI-Improvement | Glance - Special Charts | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Productivity | UI-Improvement | Action Items in multiple file upload | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH | Expecting feedback from aviation team - Sampath to revert with requirements detailing
TBD | User Experience | UI-Improvement | Provision to specify dynamic width for grid columns which have dynamic caption | Rams-Plf | Platform |  | 2022-04-01 |  |  |  | Yet To Start |  |  |  |  | TECH
TBD | Productivity | UI-Improvement | SOLR and ES Listedit in Glance | Rams-Plf | Platform |  | TBD |  |  |  | Yet To Start |  |  |  |  | TECH
TBD | User Experience | UI-Controls | Glance modeling for bulk file download as zip file | Rams-Plf | Platform | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | Productivity | MDCF | MDCF SSO | Rams-Infra | MDCF | [5 empty] | Yet To Start |  |  | TECHB-418 |  | TECH
TBD | Productivity | MDCF | MDCF - UI changes for mapping same task multiple times | Rams-Plf | MDCF | [5 empty] | Yet to Start |  |  | TECHB-661 |  | TECH
2022-09-01 | User Experience | PubSub | Usability : Publish Subscribe Efficiency | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  | TECHB-293 |  | TECH | Provision to auto default pub-sub predefined controls
TBD | Productivity | Workflow | Api for Visual Workflow Designer | Rams-Infra | Workflow | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | User Experience | Reporting | OU level precision for ARI Reports | Rams-Infra | Reporting | [5 empty] | Clarified |  |  | TECHB-675 |  | TECH | Syngenta-IMP-HCM - ???
TBD | Security | Vulnerability | Disabling FIPS compliant algorithms for encryption, hashing, and signing | Rams-Infra | Reporting | [5 empty] | Yet to Start |  |  | TECHB-671 |  | TECH
TBD | Productivity | MDCF | MDCF LDAP | Rams-Infra | MDCF | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | Productivity | MDCF | MDCF for Java Tech Stack | Rams-Infra | MDCF | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | Security | Vulnerability | Vulnerability fixation for FOSSA observations | Rams-Infra | Reporting | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | User Experience | Dcube | Pivot Grid in Dcube | Rams-Infra | DCube | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | User Experience | InBox | Provision to navigate back to InBox on successful execution of a workflow task | Rams-Plf | InBox | [5 empty] | Yet to Start |  |  | TECHB-665 |  | TECH
TBD | Productivity | Workflow | Workflow mailer service deadlock / not started - consolidated report | Rams-Infra | Workflow | [5 empty] | Yet to Start |  |  | RBE-734 |  | TECH
TBD | Productivity | Figma Import | POC for importing from Figma | Sampath | [6 empty] | Deferred |  |  |  |  | TECH
TBD | User Experience | Scheduling | Scheduling Hub - Generic Infra component | Rams-Infra | General | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade |  | Infra components certification for cluster database in different zones (Multi-subnet fail over property in connection string) | Rams-Infra | General | [5 empty] | Yet to Start |  |  |  |  | TECH
TBD | Productivity | Workflow | Time-based workflow critical defect fixes | Rams-Infra | Workflow | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | User Experience | ARI | Provision to implement template based report in ARI (dcube capablity) | Rams-Infra | Reporting | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-08-01 | Tech Upgrade | Security | Workflow/Reporting Components Mailer - O365 modern authentication instead of basic authentication | Rams-Infra | Workflow | Extra Large | 2022-07-01 | 2022-08-31 |  |  | Completed | Raja Priyaa |  | TECHB-870 |  | TECH
TBDQ | Tech Upgrade | Security | Glance Apis migration from V3 to V4 | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-10-01 | Tech Upgrade | Usablity | Decoupling daemon for time based workflow | Rams-Infra | Workflow | Extra Large | 2022-09-01 | 2022-10-31 |  |  | In Progress | Akila R |  |  |  | TECH
TBDQ | Tech Upgrade | Single DB | Approach and Changes for implementing Single DB approach | Rams-infra | General | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-09-01 | User Experience | Workflow | Approval trial UI for unify apps | Rams-Infra | Workflow | Medium | 2022-08-01 | 2022-09-30 |  |  | In Progress | Muthulakshmi |  | TECHB-897 |  | TECH
TBD | Productivity | Report | Approach for partner key /report id uniqueness | Rams-Infra | Reporting | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-08-01 | Productivity | UI-Improvement | Platform Modeling - Provision to model application pre and post task for attach document delete and browse task (Header and ML) | Rams-Plf | Platform | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Jeya |  | TECHB-871 |  | AVN
2022-07-01 | User Experience | Dcube | Dcube - Provision to specify database at view level for view type “Reports” | Rams-Infra | DCube | Large | 2022-07-01 | 2022-07-31 |  |  | Completed | Muthulakshmi |  | TECHB-887 |  | TECH
2022-08-01 | Productivity | UI-Improvement | Glance Modeling - Provision to model application pre and post task for attach document delete and browse task (Header and ML) | Rams-PlfRT | Platform | Medium | 2022-08-01 | 2022-08-31 | Yet To Start | Jeya | Hold | Giri |  | TECHB-872 |  | AVN
TBDQ | User Experience | UI-Controls | iRule implementation for conditional templates | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade | Operations | Refactoring - Eliminating Quartz and topshelf for workflow inbox monitor mdcf, workflow mailer | Rams-Infra | InBox Montior | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Productivity | UDS | Role based access for Report Authorization | Rams-Infra | Reporting | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-11-01 | User Experience | Dcube | Dcube - Support for Synonyms | Rams-Infra | DCube | Medium | 2022-09-01 | 2022-11-30 |  |  | In Progress | Uma |  |  |  | HRP
2022-11-01 | User Experience | Localization | Multilanguage Support for Dcube | Rams-Infra | DCube | Extra Large | 2022-09-01 | 2022-11-30 |  |  | In Progress | Uma |  |  |  | TECH
TBD | User Experience | Localization | Workflow admin and dcube localization (25 languages) | Rams-Infra | Workflow | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade | Operations | Glance - Upgrading Pencil to GrapeJS libraries | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Productivity | UDS | DCube Reports in UDS context ?? | Rams-Infra | DCube | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-08-01 | Tech Upgrade | Developer Experience | Report modeling enablement in platform model for GQL based user interfaces | Rams-Plf | Platform | Medium | 2022-07-18 | 2022-08-18 |  |  | Completed | Venkatesh |  | TECHB-873 |  | TECH
2022-07-01 | User Experience | UI-Controls | Platform Modeling - Provision to capture additional attributes (file size and type) for file attachment control | Rams-Plf | Platform | Medium | 2022-07-18 | 2022-08-18 |  |  | Completed | Jeya |  | TECHB-744 |  | TECH | Hidden Edit Control / Column
2022-08-01 | User Experience | UI-Controls | Glance Modeling - Provision to capture additional attributes (file size and type) for file attachment control | Rams-PlfRT | Platform | Medium | 2022-07-18 | 2022-08-18 |  |  | Hold | Giri |  | TECHB-874 |  | TECH
TBD | Tech Upgrade | Productivity | POC - Reverse engineering platform modeled UIs to Glance | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade | Developer Experience | POC - Moving glance from pencil framework to GrapeJS libraries | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | User Experience | UI-Controls | Provision to model dynamic tooltip for GQL based UI | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Productivity | Developer Experience | FITBIT enablement in all product model servers | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | User Experience | UI-Controls | Platform Modeling - Minimized Section and Sidebar | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  | TECHB-719 |  | TECH
TBD | User Experience | UI-Controls | Glance Modeling - Minimized Section and Sidebar | Rams-Plf | Platform | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Security | Vulnerability | Using SMB or TCP protocol for report file access instead of UDB port 445 | Rams-Infra | Reporting | [5 empty] | Yet To Start |  |  |  |  | TECH | SCO Gen
2022-07-01 | User Experience | ARI | ARI Scheduler - Provision to copy generated report in FTP / SFTP folder | Rams-Infra | Reporting | Medium | 2022-07-01 | 2022-07-31 |  |  | Completed | Niranjan P |  | TECHB-631 |  | TECH
2022-07-01 | User Experience | UI-Controls | Platform modeling for Sidebar | Rams-Plf | Platform | Medium | 2022-07-01 | 2022-07-31 |  |  | Completed | Jeya |  | TECHB-708 |  | TECH
2022-07-01 | User Experience | UI-Controls | Platform modeling for Minimized Section | Rams-Plf | Platform | Medium | 2022-07-01 | 2022-07-31 |  |  | Completed | Jeya |  | TECHB-888 |  | TECH
2022-08-01 | User Experience | UI-Controls | Platform modeling for Top Inner Labels | Rams-Plf | Platform | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Jeya |  | TECHB-878 |  | TECH
2022-07-01 | User Experience | UI-Controls | Glance modeling for Sidebar | Rams-PlfRT | Platform | Medium | 2022-07-01 | 2022-07-31 |  |  | Hold | Giri |  | TECHB-889 |  | TECH
2022-07-01 | User Experience | UI-Controls | Glance modeling for Minimized Section | Rams-PlfRT | Platform | Medium | 2022-07-01 | 2022-07-31 |  |  | Hold | Giri |  | TECHB-890 |  | TECH
2022-09-01 | Productivity | UDS | Reporting as Services - SP Based ER Reports | Rams-Infra | Reporting | Extra Large | 2022-07-01 | 2022-08-31 |  |  | In Progress | Niranjan P |  | TECHB-898 |  | TECH
2022-10-01 | Productivity | UDS | Reporting as Services - SSRS Reports - Register Mode | Rams-Infra | Reporting | Extra Large | 2022-08-01 | 2022-09-30 |  |  | In Progress | Niranjan P |  |  |  | TECH
2022-06-01 | Training | Platform | Device Notification training session for ERP and LGT team | Rams-Plf | Workflow | Medium | 2022-06-01 | 2022-06-30 |  |  | Completed |  |  |  | Yes | TECH
2022-07-01 | Productivity | Platform | Scripts to rollback component level ECR to any previous ECR | Rams-Plf | Platform |  | 2022-07-01 | 2022-07-31 |  |  | Hold | Jeya |  |  |  | TECH
TBD | Operation | MDCF | Feasiblity of eliminating Quartz in MDCF | Rams-Infra | MDCF | Medium |  |  | Yet To Start | [6 empty] | TECH
2022-06-01 | MDCF | GSG | GSG - Critical Defect Fixes - TECH-70183 & TECH-70184 (Provision to identify empty / null values), comma handling in csv import | Rams-Infra | GSG | Medium | 2022-06-01 | 2022-06-30 | 2022-06-30 |  | Completed | Akila R |  |  | Yes | TECH
2022-07-01 | Productivity | UI-Improvement | Allow to Create Single/Multi Marker based on Option -> default - Multiple | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | UI-Improvement | Click on create marker action required -> true / false | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | UI-Improvement | Markers with Custom Label on Bottom | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | UI-Improvement | File Type, File Size based on options in fileupload - > header and multi | Sampath |  | Medium | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | UI-Improvement | Stepper Control | Sampath |  | Medium | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | Template Columns | Sampath |  | Medium | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | Header Assorted Controls (Tile with templates) | Sampath |  | Medium | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Import Excel - Server Side | Sampath |  | Large | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Export to Excel - Server Side | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Export to CSV - Server Side | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Export to HTML - Server Side | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Export to PDF - Server Side | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Export to TXT - Server Side | Sampath |  | Small | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Productivity | GQL | ML Syncview (Listedit) | Sampath |  | Medium | 2022-07-01 | [8 empty] | TECH
2022-07-01 | Operation | Reports | Moving YTD & Salary Register from ARI to alternate report source (Benchmarking memory utilization) | Rams-Infra | Reporting | Large | 2022-07-01 | 2022-08-31 | Yet To Start |  | In Progress | Akila R |  | TECHB-891 |  | HRP
2022-07-01 | User Experience | UI-Controls | Platform modeling - Provision to allow items from available list only for list edit controls | Rams-Plf | Platform | Low | 2022-07-01 | 2022-07-31 |  |  | Completed | Jeya |  | TECHB-892 |  | ERP
2022-08-01 | User Experience | UI-Controls | Glance modeling provision to allow listedit controls to select values from allowed list values only | Rams-PlfRT | Platform | Low | 2022-08-01 | 2022-08-31 |  |  | Hold | Giri |  | TECHB-875 |  | ERP
TBD | User Experience |  | Provision to copy zipped file to SFTP | Rams-Infra | Reporting | Medium |  |  |  |  | Yet to Start |  |  |  |  | HRP
2022-08-01 | User Experience | UI-Controls | Platform Modeling - Section Title Icon | Rams-Plf | Platform | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Jeya |  | TECHB-876 |  | ERP
2022-08-01 | User Experience | UI-Controls | Platform Modeling - Button Style for DisplayOnly and Data Hyper Link Control | Rams-Plf | Platform | Low | 2022-08-01 | 2022-08-31 |  |  | Completed | Jeya |  | TECHB-723 |  | ERP
2022-08-01 | User Experience | UI-Controls | Glance Modeling - Section Title Icon | Rams-PlfRT | Platform | Low | 2022-08-01 | 2022-08-31 |  |  | Hold | Giri |  | TECHB-877 |  | ERP
2022-08-01 | User Experience | UI-Controls | Glance Modeling - Button Style for DisplayOnly Control | Rams-PlfRT | Platform | Low | 2022-08-01 | 2022-08-31 |  |  | Hold | Giri |  | TECHB-723 |  | ERP
2022-08-01 | Operation | Security | Deployment metadata script generator changes for Security permissions for Export to excel | Rams-Plf | Platform | Medium | 2022-08-01 | 2022-08-31 |  |  | Hold | Venkatesh |  |  |  | TECH | Required script already available
2022-08-01 | Reports | Security | Vulnerablity - Broken Access Control - Privilege Escalation Attack - A low-privileged user, by parameter manipulation, can gain accessto the application as a high-privileged user or perform malicious activities posing as another user | Rams-Infra | Reporting | Large | 2022-08-01 | 2022-08-31 |  |  | Completed | Niranjan / Uma |  | TECHB-879 |  | ERP | ICICI Bank
2022-08-01 | Reports | DCube | Dcube - Export to PDF - Licensed component identification for converting word to PDF (ASPOSE) - POC for ASOPOSE | Rams-Infra | DCube | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Uma |  | TECHB-880 |  | TECH
TBD | Usability | Workflow | Enable workflow screen 1) Save to be optimized with process only modified rows (ML Save taking longer time for 700 OUs) 2) Additional filter (OU Description) to fetch ML | Rams-Infra | [6 empty] | Yet to Start | Uma |  |  |  | DLF
2022-09-01 | Usability | Mail IT | Multi-Language support for Mail IT | Rams-Infra | Mail IT | Medium | 2022-08-01 | 2022-09-30 |  |  | In Progress | Uma |  |  |  | HRP | Sodexo
2022-08-01 | Productivity | UI-Improvement | Platform Modeling - Badge Property for DataHyperLink | Rams-Plf | Platform | Low | 2022-08-01 | 2022-08-31 |  |  | Completed | Jeya |  | TECHB-881 |  | ERP
2022-08-01 | Operation | Review | ECR difference report | Rams-Plf | Platform | High | 2022-08-01 | 2022-09-30 |  |  | In Progress | Jeya |  | TECHB-248 |  | AVN
2022-07-01 | Operation | Productivity | Integerating iRule xml generator in main stream code generator | Rams-Plf | Platform | Medium | 2022-07-01 | 2022-07-31 |  |  | Completed | Madhan |  | TECHB-893 |  | ERP
2022-08-01 | Operation | Productivity | Provision to upload mobility config xml, template and CSS into model and integerating with mobility code generator | Rams-Plf | Platform | Medium | 2022-07-20 | 2022-08-31 |  |  | Completed | Madhan |  | TECHB-883 |  | ERP
2022-08-01 | User Experience | UI-Controls | Glance Modeling - Badge Property for DataHyperLink | Rams-PlfRT | Platform | Medium | 2022-08-01 | 2022-09-30 | In Progress | Jeya | Hold | Giri |  | TECHB-882 |  | ERP
2022-08-01 | Operation | Reports | ER Service based Report - XLS Raw data - Provision to exclude segment name in column title | Rams-Infra | Reporting | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Akila R |  | TECHB-855 |  | AVN
2022-08-01 | Operation | GSG | Request for adding Sequence_no in both GSG MDCF and GSG Download services | Rams-Infra | GSG | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Akila R |  | TECH-71518 |  | HRP
2022-08-01 | Adaptability | DCube | DCube changes for accommodating large audit trail report (base table having around 400 columns) | Rams-Infra | DCube | Medium | 2022-08-01 | 2022-08-31 |  |  | Completed | Vigneshwari S |  | TECHB-885 |  | LGT
2022-07-01 | User Experience | ER Reports | Provision to move ER (Split delivery) zipped file to STFP | Rams-Infra | Reporting | Medium | 2022-07-01 | 2022-07-31 |  |  | Completed | Akila R |  | TECHB-894 |  | HRP | Global Foundaries
TBD | Cost | PowerBI | Approach for Managing License count for Power BI | Rams-Infra | Reporting | High |  |  |  |  | Yet To Start | Niranjan |  |  |  | PCO
2022-11-01 | User Experience | UI-Controls | Platform modeling for Stepper Control | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | In Progress | Venkatesh |  |  |  | ERP
TBD | User Experience | UI-Controls | Glance modeling for Stepper Control | Rams-PlfRT | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Yet To Start | Giri |  |  |  | ERP
TBD | User Experience | UI-Controls | Platform modeling for mouse hover popup section | Rams-Plf | Platform | Medium |  |  |  |  | Yet to Start | Jeya |  |  |  | ERP
2022-09-01 | User Experience | UI-Controls | Glance modeling for mouse hover popup section | Rams-PlfRT | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Hold | Giri |  |  |  | ERP
2022-09-01 | Productivity | GQL | GQL - System testing for GQL Phase-3 | Rams-Plf | Platform | High | 2022-08-20 | 2022-09-30 |  |  | In Progress | Venkatesh |  | TECHB-899 |  | TECH
2022-11-01 | Security | Vulnerability | CSP Changes for Reporting Components | Rams-Infra | Reporting | High | 2022-08-16 | 2022-10-31 |  |  | In Progress | Niranjan / Uma |  |  |  | LGT
TBD | Security | Vulnerability | Vulnerablity - Broken Access Control - Privilege Escalation Attack - Fixation for drill through reports | Rams-Infra | Reporting | High | 2022-08-16 | 2022-08-31 |  |  | Yet to Start | Niranjan / Uma |  | TECHB-886 |  | ERP
TBD | User Experience | PowerBI | Provision to launch power BI reports from application screen | Rams-Infra | Reporting | High |  |  |  |  | Yet To Start | Niranjan |  |  |  | PCO
TBD | User Experience | PowerBI | Provision to pass different user & role name (currently context user and role) to power bi dataset | Rams-Infra | Reporting | Medium |  |  |  |  | Yet To Start | Niranjan |  |  |  | PCO
2022-09-01 | Tech Upgrade | Java | Java code generator changes for JDK 11 (JPMC Migration) | Rams-Plf | Platform | Medium | 2022-08-16 | 2022-09-30 |  |  | Completed | Madhan |  | TECHB-900 |  | TECH | JPMC Project
2022-10-01 | User Experience | GSG | GSG - File adapters for Azure container (feasibility to read and write file from azure containers) | Rams-Infra | GSG | High | 2022-09-01 | 2022-10-31 |  |  | In Progress | Uma |  |  |  | HRP | Sodexo
2022-10-01 | User Experience | UI-Controls | Productivity: Default Required Option in ML: Default Required Option in ML: Defaults required property of a multiline column should be automatically selected for editable and combo controls. Now there are old screens having multilines which can be enabled with this option at once for the existing multilines.For new screens when the multiline is added, most cases, this property is missed to be selected. Hence auto selection of this property is required. | Rams-Plf | Platform | Medium | 2022-10-01 | 2022-10-31 |  |  | In Progress | Jeya |  | TECHB-266 |  | AVN
2022-09-01 | User Experience | UI-Controls | Platform Modeling - Auto Height for Grid Control | Rams-Plf | Platform | Low | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  | TECHB-235 |  | AVN
TBD | User Experience | UI-Controls | Glance Modeling - Auto Height for Grid Control | Rams-Plf | [6 empty] | Yet to Start |  |  | TECHB-235 |  | AVN
2022-09-01 | Productivity | Training | L1 - Assessment Questions till engineering | Rams-Plf | Platform | High | 2022-09-01 | 2022-09-30 |  |  | In Progress | Jeya |  |  |  | LD
2022-09-01 | Productivity | Hygiene | Context user names in design tables | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | Hygiene | Aviation performance optimization | Rams-Plf | Platform | High | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | Hygiene | Analysis for hidden control creation | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | In Progress | Jeya |  |  |  | TECH
2022-09-01 | Process | Traceablity | Provision to specify feature id and rTrack case id in document creation activity | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | Metrics | Developer Productivity Metrics | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
TBD | User Experience | Productivity | Provision to export report schedule information in report metadata generation | Rams-Infra | Reporting | Medium |  |  |  |  | Yet To Start | Uma |  |  |  | TECH
2022-09-01 | User Experience | Configuration | Analysis for excluding return url in report configuration | Rams-Infra | Reporting | Medium | 2022-09-01 | 2022-09-30 |  |  | In Progress | Uma |  |  |  | TECH
2022-09-01 | User Experience | Usablity | Feasiblity check for dcube execution report with report name using depdb audit activity and mini profiler data | Rams-Infra | DCube | Medium | 2022-09-01 | 2022-09-30 | In Progress | Uma | Completed | Uma |  |  |  | AVN
TBD | Tech Upgrade | Usablity | Model Explorer - Migration to newer TECH Stack | Rams-Plf | Model Explorer | High |  |  |  |  | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade | Usablity | Dcube migration tool - Migration to newer TECH Stack | Rams-Infra | DCube | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade | Usablity | Audit trial - Migration to newer TECH Stack | Rams-Infra | Audit Trial | [5 empty] | Yet To Start |  |  |  |  | TECH
TBD | Tech Upgrade | Usablity | WF mail link code generator - Migration to newer TECH Stack | Rams-Infra | Workflow | [5 empty] | Yet To Start |  |  |  |  | TECH
2022-09-01 | Productivity | iEDK Exceptions | Uniqueness of BT Synonym, Precision Type, BT Name, Method Name, Service Name and Error ID at customer project level for newly created entities only | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | iEDK Exceptions | Recheck of system generated BT Synonym and restricting to max 30 characters | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | iEDK Exceptions | Restricting segment name to 30 characters for newly created segments | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | iEDK Exceptions | Restricting SP name to 30 characters for newly created segments | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | iEDK Exceptions | Validation for new line character in error messages | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-09-01 | Productivity | iEDK Exceptions | ECR Publish - Data consistency in fw_des_ilbo_service_view_datamap and fw_des_ilbo_service_view | Rams-Plf | Platform | Medium | 2022-09-01 | 2022-09-30 |  |  | Completed | Jeya |  |  |  | TECH
2022-11-01 | Quality | Platform | Quality: Tool to review the delta changes of ECR | Rams-Plf | Platform | Medium | 2022-08-15 | 2022-11-30 |  |  | In Progress | Jeya |  | TECHB-248 |  | TECH
TBD | Tech Upgrade | Jasper-Upgrade | ER reports has to be certified in the latest version of Jasper libraries v6.20.0 (Current 6.16.0) | Rams-Infra | Reporting | Medium | [9 empty] | TECH
2022-10-01 | Quality | Productivity | Control type definition should be within that screen level ( changing the property of existing old control type it affect others screen in that component wherever it has been used already) - Can be planned - Based on system parameter validation will be raised if a control type is reused across screens and requirements engineer trying to change control properties | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-10-31 |  |  | In Progress | Jeya |  |  |  | HRP
2022-10-01 | Quality | Productivity | Need validation while moving controls/column from main section to hidden section if it already involved in state processing | Rams-Plf | Platform | Low | 2022-10-03 | 2022-10-31 | In Progress | Jeya | In Progress | Jeya |  |  |  | HRP
2022-11-01 | Operation | Productivity | Automatic hdn view mapping For Combo Controls while defining the combo controls (to avoid one additional step of doing manual hdn view creation and mapping to combo controls ) - Can be planned - Based on system parameter for hidden views will be auto populated based for new combo controls | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | Yet To Start | Jeya |  |  |  | HRP
2022-11-01 | Operation | Productivity | Automatic mapping of hdn views mapping to all task (to avoid one additional step of doing manual hdn view mapping to all required task ) . Can be planned - Based on system parameter for new services (pattern based generation only - and not for refine or define (manual) service - When base control is mapped automatically hidden view will also be included for service generation | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | Yet To Start | Jeya |  |  |  | HRP
2022-11-01 | Operation | Productivity | IF RVW allows for SetupUI preference->Action Pattern edits at in Design layout level also (if not used in other activities) it would be better. Setup Preference activity to moved from Solutioning to Engineering | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | Yet To Start | Jeya |  |  |  | HRP
2022-11-01 | Operation | Productivity | Usability : Publish Subscribe Efficiency - Publish Subscribe Efficiency Currently, common controls like OUCode, Source Context, GUID etc., needs to be manually published - subscribed to the link or help screens. Since these controls are common across user interfaces, when any link or help is provided, can we automatically have them published and subscribed, if we are willing to go with standard naming of the controls >> APRP-1184 | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | In Progress | Jeya |  |  |  | AVN
2022-12-01 | Quality | Productivity | Need validation / intimation of update service done already for that generated service (to avoid mistake in reuse of sp/method )- ECR Publish - Validation to ensure update service is done | Ram-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet To Start | Jeya |  |  |  | HRP
2022-12-01 | Quality | Productivity | Need validation when ILBO association not done for a Control in manual design (to avoid issues in runtime ) - Can be planned only if a control is not mapped to any service in ILBO | Ram-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet To Start | Jeya |  |  |  | HRP
2022-12-01 | Quality | Productivity | Need validation when SP is reused across the services and forgot to regenerate other the impacted services - to avoid parameter mismatch across the Service when SP is reused - ECR Publish - Validation to ensure update service is done | Ram-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet To Start | Jeya |  |  |  | HRP
TBD | User Experience | Productivity | In Refine service need to show the count of method mapped under that service before & after the update service (to avoid the mismatch of method count before and after the regeneration of services ) | Rams-Plf | Platform | High |  |  |  |  | Yet To Start | Jeya |  |  |  | HRP
2022-10-01 | Quality | Productivity | When email to be reconfigured, the data is lost and have to do it again (engine workflow, direct workflow, time based ) | Rams-Infra | Workflow | Medium | 2022-10-01 | 2022-10-31 |  |  | In Progress | Uma |  |  |  | LGT
2022-10-01 | Usability | Productivity | MDCF - generate template (TDCF), timeout error | Rams-Infra | MDCF | Low | 2022-10-01 | 2022-10-31 |  |  | Yet To Start | Uma |  |  |  | LGT
2022-10-01 | Usability | Productivity | Reports - share report to ftp instead of sftp | Rams-Infra | Reporting | Low | 2022-10-01 | 2022-10-31 |  |  | Yet To Start | Uma |  |  |  | LGT
2022-11-01 | Reuseablity | Productivity | Service based report - unable to schedule (due to duplicate BT synonymn) | Rams-Infra | Reporting | High | 2022-10-01 | 2022-11-30 |  |  | Yet To Start | Uma |  |  |  | ERP
2022-11-01 | Operation | Productivity | Export to XLS data - column sizes are varying, word wrap etc. Can this be standardized and aligned - Reports - aligned the report for pdf but the pdf gets alignment issue | Rams-Infra | Reporting | Medium | 2022-10-01 | 2022-11-30 | Yet To Start |  | Yet To Start | Uma |  |  |  | ERP, LGT
2022-11-01 | Operation | Productivity | Reports - comma separator for numeric fields(1000) - export to csv breaks the columns | Rams-Infra | Reporting | Medium | 2022-10-01 | 2022-11-30 |  |  | Yet To Start | Niranjan |  |  |  | LGT
2022-12-01 | Reuseablity | Productivity | HOD should approve a sp is written, since SP resuse is not there they have to write sp for each use case | Rams-Infra | Workflow | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Uma |  |  |  | ERP
2022-12-01 | User Experience | Productivity | Next gen workflow - criteria tab unable to clear filters | Rams-Infra | Workflow | High | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Uma |  |  |  | LGT
2022-12-01 | Configuration | Productivity | Reports - devs hard code logos, should come from configuration | Rams-Infra | Reporting | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Uma |  |  |  | LGT
TBD | Bulk Operations | Productivity | MDCF for workflow configurations | Rams-Infra | Workflow | High | [5 empty] | Uma |  |  |  | ERP
TBD | Bulk Operations | Productivity | MDCF for workflow rule configurator | Rams-Infra | Workflow | High | [5 empty] | Uma |  |  |  | HRP
TBD | Operation | Productivity | Org Structure based workflow approval | Rams-Infra | Workflow | High | [5 empty] | Uma |  |  |  | ERP
TBD | Logging | Productivity | Workflow enginee SPs - Traceablity and trouble shooting logs in backend table | Rams-Infra | Workflow | High | [5 empty] | Uma |  |  |  | LGT
TBD | Operation | Productivity | Duplicate caption handling in MDCF template generator and runtime | Rams-Infra | MDCF | High | [5 empty] | Uma |  |  |  | LGT
2022-11-01 | Tech Upgrade | License | ASPOSE integeration for ducbe template based reports | Rams-Infra | DCube | Medium | 2022-10-01 | 2022-11-30 |  |  | Yet To Start | Uma |  |  |  | HRP
2022-10-01 | Operation | Logging | Table Based MDCF - Logger enhancements with request payload for failure events | Rams-Infra | MDCF | Medium | 2022-10-01 | 2022-10-31 |  |  | In Progress | Uma |  |  |  | HRP | LendLease
2022-12-01 | Operation | Productivity | Need validation / intimation of update service done already for that generated service (to avoid mistake in reuse of sp/method ) | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | HRP
2022-12-01 | Operation | Productivity | Need validation when ILBO association not done for a Control in manual design (to avoid issues in runtime ) - Can be planned only if a control is not mapped to any service in ILBO | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | HRP
2022-12-01 | Operation | Productivity | Need validation when SP is reused across the services and forgot to regenerate other the impacted services (to avoid parameter mismatch across the Service when SP is reused ) | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | HRP
TBD | Operation | Productivity | in Refine service need to show the count of method mapped under that service before & after the update service (to avoid the mismatch of method count before and after the regeneration of services ) | Rams-Plf | Platform | High |  |  |  |  | Yet to Start | Jeya |  |  |  | HRP
2022-10-01 | User Experience | UI-Controls | Platform Modeling - Eye icon for password control (Need "xtype": "ramcopassword" and "showIcon": true property in modelling to enable Eye icon) | Rams-Plf | Platform | Low | 2022-10-01 | 2022-10-31 |  |  | In Progress | Jeya |  | TECHB-916 |  | HRP
2022-10-01 | User Experience | UI-Controls | Platform Modeling - Provision to associate display control to muliselect combo for displaying selected items | Rams-Plf | Platform | Low | 2022-10-01 | 2022-10-31 |  |  | In Progress | Jeya |  |  |  | AVN
2022-10-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify Signature Field for Mobility UI's (base control type - edit, editable - yes) | Rams-Plf | Platform | Medium | 2022-10-01 | 2022-10-31 |  |  | In Progress | Jeya |  |  |  | Mobility
2022-10-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify Keyup Search for edit fiels - Applicable only for offline mobility UI's | Rams-Plf | Platform | Medium | 2022-10-01 | 2022-10-31 |  |  | In Progress | Jeya |  |  |  | Mobility
2022-10-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify Back count for button control when Previous Button property is enabled | Rams-Plf | Platform | Low | 2022-10-01 | 2022-10-31 |  |  | In Progress | Jeya |  |  |  | Mobility
2022-11-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify stepper for numeric edit control (with min, max and step value) | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | In Progress | Jeya |  |  |  | Mobility
2022-11-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify Live Clock - Applicable for base control type - displayonly & datatype should be - time, datetime | Rams-Plf | Platform | Medium | 2022-10-03 | 2022-11-30 |  |  | In Progress | Jeya |  |  |  | Mobility
2022-12-01 | User Experience | UI-Controls | Platform Modeling - Provision to Pull To Refresh - UI Property for mobility Uis | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | Mobility
2022-12-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify clear task for edit field | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | Mobility
2022-12-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify progress bar (base control type - RsSlidder with min, max and step value) | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | Mobility
2022-12-01 | User Experience | UI-Controls | Platform Modeling - Provision to specify animation for data grid | Rams-Plf | Platform | Medium | 2022-11-01 | 2022-12-31 |  |  | Yet to Start | Jeya |  |  |  | Mobility
Note on N1: Man Days Keep this less than 15. Break up if something goes beyond 15

## Support Action Items
Report Configuration Documents
ER
ARI - Report Desgin Document
Trouble Shooting Docs
Do's and Dont's
Logger Enhancements
Report Schedule Export
Partner Code
Artifacts configuration managed
Return URL | Sep
Memory Requirements
If token is not available for PDF split, need to raise a valid error. | Sep
Schedule document must be enhanced with the prerequisites like Config changes as below. <add key="SCH_DOMAIN" value="LP8647" /> <add key="SCH_USERNAME" value="TechAdmin" /> <add key="SCH_ENC_PASSWORD" value="dfsbcvjmgn /GWaEI=" /> <add key="SMTP_SERVER" value="smtp.office365.com" /> <add key="SMTP_SMTPSERVERPORT" value="587" /> <add key="SMTP_USESSL" value="true" /> <add key="SMTP_SENDUSERNAME" value=abc@ramco.com /> <add key="SMTP_SENDPASSWORD" value="abc123" /> <add key="FROM_MAIL_ADDRESS" value=abc@ramco.com />
The below config changes also need to be added in the schedule document. For single tenant: a. Copy ConnectionInfo.config, Sqlmap.config and providers.config from \\VirtualWorks\VWService and deploy it into \\VirtualWorks\VWService\bin folder. For multi-tenant : a. Copy ConnectionInfo.config, Sqlmap.config and providers.config from \\VirtualWorks\VWService and deploy it into \\VirtualWorks\VWService\bin folder. b. .Kindly add the tenant RM details in the connectioninfo.config file in the path VirtualWorks\VWService\bin
If schedule SP does not return the result set a valid error has to be thrown and shown in the screen/table.
If any report SP related error occurs the same has to be shown in the screen/table.
Python version and installation steps has to be added.
For PDFsplit route - schedule status must be shown in the front end in manage schedule screen/status screen.
This error must be changed and show the proper error message. Invalid parameter name, The name of the parameter (case sensitive) is the same as an existing parameter. The actual parameter name is : 'hrpaycalend_hdnvw'. | Sep
Additional log information in case any failure in MDCF tasks | Oct
Valid in next-gen workflow (runtime sp) when there is mismatch between view definition in application db and view definition in workflow db
Export to excel - Column width management
Time based workflow - Select Process - ngwf_mgtcfg_ngwf_mgtcfg_selproce screen - last column action to be hidden | Oct
Time based workflow - Maintain Message - ngwf_cfgmsg_ngwf_cfg_msgdefex - format tab (functionality unknown) to be hidden | Oct
Time based workflow - task dll logger to be enhanced | Oct
Time based workflow - Resouce details - Server name, user id and password - useage to be identified (with MSDTC removal this may not be applicable)
Time based workflow - Maintain Message - Save functionality for all tabs to be verified
Dcube template based report - logger to be enhanced
DCube - Dynamic Filter - Parameter value help screen - Help - multiple return values to be stopped
DCube - Define View - Specify procedures inputs - Help - multiple return values to be stopped
InBox Monitor - POP3 - Read mail messages must be moved to seperate folder
InBox Monitor - POP3 - JSON - Cummalative json operation to be refactored | Oct
DCube - ML Parameter help - Help screen should be restricted to select only 1 row in ML (Usablity issue)

## Archive
Sprint | Benefit | Theme | Work Item (User Story) | Unit | PSD | OPED | CPSD | CPED | Status | Estimate | rTrack ID | Unplanned | Requestor | Project | Remarks
2021-08-01 | Productivity | Task-Api | Provision to map one or more Api operation to an task | Rams-Plf | 2021-08-02 | 2021-08-18 |  |  | Completed | 25 | TECHB-540 |  | ERP
2021-08-01 | Productivity | Task-Api | Provision to define sub-task and map to an main task | Rams-Plf | 2021-08-02 | 2021-08-18 |  |  | Completed | 15 | TECHB-540 |  | ERP
2021-08-01 | Productivity | Task-Api | Provision to map Api parameters to parameter, request and response | Rams-Plf | 2021-08-06 | 2021-08-25 |  |  | Completed | 35 | TECHB-540 |  | ERP
2021-08-01 | Productivity | Task-Api | Code generator changes for invoking Api from web layer | Rams-Plf | 2021-08-05 | 2021-08-25 |  |  | Completed | 40 | TECHB-541 |  | ERP
2021-08-01 | Productivity | Glossary | Glossary refinements for Multilanguage | Rams-Plf | 2021-08-10 | 2021-08-31 |  |  | Completed | 10 | TECHB-539 |  | HRP
2021-08-01 | Productivity | Glossary | Glossary - BT Synonym Bulk Excel upload tool | Rams-Plf | 2021-08-20 | 2021-08-27 |  |  | Completed | 5 | TECHB-563 | Y | ERP
2021-08-01 | Tech Upgrade | Jasper-Upgrade | Code Changes & Testing - ER reports has to be certified in the latest java/open JDK version | Rams-Infra | 2021-08-05 | 2021-08-19 |  |  | Completed | 15 | TECHB-527 |  | TECH |  | Jasper 6.16 - Open JDK 11 - Testing InProgress Jasper 6.16 - Open / Java JDK 11
2021-08-01 | Tech Upgrade | Jasper-Upgrade | Code Changes for Latest Jasper version upgrade | Rams-Infra | 2021-08-09 | 2021-08-20 |  |  | Completed | 20 | TECHB-527 |  | TECH
2021-08-01 | Tech Upgrade | Jasper-Upgrade | Designer Verification with latest version (Design Property, Excel Property and Control Rendering Validation) | Rams-Infra | 2021-08-16 | 2021-08-25 |  |  | Completed | 15 | TECHB-527 |  | TECH
2021-08-01 | Tech Upgrade | Jasper-Upgrade | Testing - Online Report - SP & Service based report | Rams-Infra | 2021-08-23 | 2021-09-03 |  |  | Completed | 15 | TECHB-527 |  | TECH
2021-08-01 | Cost | PowerBI | POC for launching reports from Power BI Report Server | Rams-Infra | 2021-08-02 | 2021-08-10 |  |  | Completed | 15 | TECHB-533 |  | TECH |  | Approach finalized - 1 use-case with same domain completed - cross domain and configuration changes to be planned Feasibility completed - Analysis service dashboard cannot be used in Report Server if 1) shared data source used
2021-08-01 | Productivity | SSRS | POC and Approach for SSRS multiple data source | Rams-Infra | 2021-08-04 | 2021-08-13 |  |  | Completed | 10 | TECHB-531 |  | HRP
2021-08-01 | Productivity | SSRS | Code Changes for SSRS multiple data source at folder level - Runtime | Rams-Infra | 2021-08-16 | 2021-09-03 |  |  | Completed | 25 | TECHB-531 |  | HRP |  | Will vary depending approach
2021-08-01 | User Experience | UI-Improvement | DW Report - Manage settings - Increasing number for visible rows to 20 | Rams-Infra | 2021-08-05 | 2021-08-06 |  |  | Completed | 2 | TECHB-524 |  | AVN
2021-08-01 | User Experience | UI-Improvement | DW Report - Manage Reports - Increasing number for visible rows to 20 | Rams-Infra | 2021-08-09 | 2021-08-10 |  |  | Completed | 2 | TECHB-525 |  | AVN
2021-08-01 | User Experience | UI-Improvement | DW report configuration - Increasing report name field to 50 characters | Rams-Infra | 2021-08-10 | 2021-08-13 |  |  | Completed | 4 | TECHB-526 |  | AVN
2021-08-01 | Security | Configuration | Schema provision to exclude reports @role-ou and user-Ou level in manage reports screen | Rams-Infra | 2021-08-18 | 2021-08-26 |  |  | Completed | 28 | TECHB-559 | Y | HRP
2021-08-01 | User Experience | Visual-Designer | Evaluation of jointJS (Rappid) for visual work flow visual configurator | Rams-ET | 2021-07-28 | 2021-08-06 |  |  | Completed | 30 | TECHB-510 |  | TECH
2021-08-01 | User Experience | Visual-Designer | Evaluation of DHTMLX for visual work flow visual configurator | Rams-ET | 2021-08-03 | 2021-08-13 |  |  | Completed | 30 | TECHB-511 |  | TECH
2021-08-21 | User Experience | KitchenSink | Grid Enhancement - Copy & Paste from EXCEL | Sampath | 2021-08-05 | 2021-08-18 |  |  | Completed | 10 | TECHB-543 |  | Nebula
2021-08-21 | User Experience | Responsive UI | Responsive UI - POC | Sampath | 2021-08-05 | 2021-08-18 |  |  | Completed | 10 | TECHB-542 |  | Nebula
2021-08-21 | User Experience | Responsive UI | Responsive UI | Sampath | 2021-08-18 | 2021-08-27 | 2021-09-01 | 2021-09-06 | Completed | 8 | TECHB-542 |  | Nebula
2021-08-21 | User Experience | Responsive UI | Responsive UI - Code generation | Sampath | 2021-08-23 | 2021-08-27 | 2021-09-01 | 2021-09-06 | Completed | 5 | TECHB-542 |  | Nebula
2021-08-21 | Tech Upgrade | mHub | mHub enablement For Android | Sampath | 2021-08-04 | 2021-08-18 |  |  | Completed | 10 | TECHB-500 |  | ERP & HCM
2021-08-21 | Tech Upgrade | mHub | mHub enablement For IOS | Sampath | 2021-08-04 | 2021-08-18 | 2021-09-01 |  | Completed | 10 | TECHB-500 |  | ERP & HCM
2021-08-21 | Tech Upgrade | mHub | mHub enablement Client Runtime | Sampath | 2021-08-04 | 2021-08-18 | 2021-09-01 |  | Completed | 5 | TECHB-500 |  | ERP & HCM
2021-08-21 | Tech Upgrade | CSP | Content Security Policy - CSP POC | Sampath | 2021-08-04 | 2021-08-31 | 2021-09-06 | 2021-09-24 | Completed | 10 | TECHB-502 |  | HCM
2021-08-01 | User Experience | InBox | Work flow InBox - Phase-1 - Interface Stored Procedures for Populating InBox Data | Rams-Infra | 2021-08-05 | 2021-08-20 |  |  | Deferred | 10 |  |  | MGMT
2021-08-01 | User Experience | InBox | Work flow InBox - Phase-1 - Backend Construction | Rams-Infra | 2021-08-05 | 2021-09-03 |  |  | Deferred | 44 |  |  | MGMT
2021-08-01 | User Experience | InBox | Work flow InBox - Phase-1 - Visual Design - Client Side Changes | Rams-ET | 2021-08-05 | 2021-09-03 |  |  | Deferred | 45 |  |  | MGMT |  | Scope of work yet to be finalized
2021-09-01 | Productivity | API | Workflow configuration metadata as API | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Deferred | 20 | TECHB-582 |  | ERP
2021-09-01 | Productivity | SSRS | Code Changes in Import tool for SSRS multiple data source at folder level | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 30 | TECHB-566 |  | HRP
2021-09-01 | User Experience | Audit Report | Audit Reports in ARI | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 15 | TECHB-558 |  | HRP | SNPL
2021-09-01 | Productivity | ANA | Provision to Export ANA data (NGWF - Event-based) | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 5 | TECHB-557 |  | LGT
2021-09-01 | Tech Upgrade | MSDTC Removal | ER Reports MSDTC Removal - OLEDB connection object changes | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 30 | TECHB-567 |  | TECH
2021-09-01 | User Experience | UI-Improvement | Provision to view ALL report types (along with report type and report name in multi line) in manage schedule and view schedule screen | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 10 | TECHB-560 |  | AVN
2021-09-01 | User Experience | UI-Improvement | Provision to display report frequency in multi line in manage schedule and view schedule screen | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 15 | TECHB-561 |  | AVN
2021-09-01 | User Experience | UI-Improvement | Suffixing timestamp to scheduled report files name based on system parameter | Rams-Infra | 2021-09-01 | 2021-09-30 |  |  | Completed | 10 | TECHB-569 |  | AVN
2021-09-01 | User Experience | Configuration | Workflow - Concept and Approach Finalization for Automatic rerouting based on document aging days | Rams-Infra | 2021-09-01 | 2021-09-15 |  |  | Completed | 5 | TECHB-568 |  | HRP
2021-09-01 | User Experience | Configuration | Workflow configuration screen for generating Actionable Notification Configuration JSON | Rams-Infra | 2021-09-15 | 2021-09-30 |  |  | Completed | 10 | TECHB-608 |  | LGT
2021-09-01 | Productivity | UI-Improvement | Glance - Metadata additions for layout property, label alignment and button nature | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 20 | TECHB-564 |  | TECH
2021-09-01 | Tech Upgrade | Packaging | Packaging and Release testing of platform components for 2.8.0.0 release | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 10 | TECHB-614 |  | TECH
2021-09-01 | Productivity | UI-Improvement | Publish RCN - Links Linkage to download ECR from publish RCN based worklist screen is missing. It would be easier to navigate to download ECR from the Publish RCN screen itself. >> APRP-1191 | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 15 | TECHB-267 |  | AVN
2021-09-01 | Tech Upgrade | MSDT Removal | MSDTC - dependency removal testing for eZee Wizard component | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 20 | TECHB-549 |  | TECH
2021-09-01 | Productivity | Test Automation | Changes in test complete generators for specifying required number of rows for grid control | Rams-Plf | 2021-09-13 | 2021-09-16 |  |  | Completed | 3 | TECH-52951 | Y | AVN
2021-09-01 | Productivity | UI-Improvement | Glance Hardening - 1) Resolve Listedit changes 2) Code gen changes referring to published ECR | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 20 | TECHB-565 |  | TECH
2021-09-01 | Tech Upgrade | Packaging | Java code generator changes for Ext JS6.x web level package of Tomcat8.5 application server | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 15 | TECHB-548 |  | JPMC
2021-09-01 | User Experience | UI-Improvement | Post API for adding new BT Synonym in Glance | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 20 | TECHB-579 |  | TECH
2021-09-01 | User Experience | UI-Improvement | Glance - New layout and behaviour attributes 1)responsiveCol for section and controls 2)isSplit for combo 3)selectColumn and dataScroller for horizontal and vertical tiles 4)isDefault for all template nodes 5)menuButton for horizontal, vertical tile and grid control 6)control type “action” for grid columns | Rams-Plf | 2021-09-01 | 2021-09-30 |  |  | Completed | 30 | TECHB-605 |  | TECH
2021-09-01 | Productivity | MDCF | Caption column addition in multiline for table based template specification | Rams-Plf | 2021-09-15 | 2021-09-30 |  |  | Completed | 20 | TECHB-613 | Y | HRP
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Multi Column - Multi Select List (React) | Rams-ET | 2021-09-01 | 2021-09-08 |  |  | Completed | 12 | TECHB-581 |  | TECH
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Nested Property Window (User Configuration - One user to be mapped to multiple proxy user) | Rams-ET | 2021-09-08 | 2021-09-10 |  |  | Completed | 15 | TECHB-581 |  | TECH
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Rule Builder | Rams-ET | 2021-09-13 | 2021-09-15 |  |  | Completed | 15 | TECHB-581 |  | TECH
2021-09-01 | Productivity | Workflow Designer | Visual Workflow Configurator - Error pane to display multiple error message | Rams-ET | 2021-09-16 | 2021-09-18 |  |  | Completed | 13 | TECHB-581 |  | TECH
2021-09-01 | Productivity | UI-Improvement | PLF change Discuss with rams ( Header tooltip, Button Menu, Dataview) | Sampath | 2021-09-08 | 2021-09-08 |  |  | Completed | 1
2021-09-01 | Productivity | UI-Improvement | Header Control Tool Tip | Sampath | 2021-09-09 | 2021-09-13 |  |  | Completed | 3 | TECHB-583 |  | Nebula
2021-09-01 | Productivity | UI-Improvement | Button Menu | Sampath | 2021-09-09 | 2021-09-10 |  |  | Completed | 2 | TECHB-584 |  | Nebula
2021-09-01 | Productivity | UI-Improvement | Grid Button Menu | Sampath | 2021-09-10 | 2021-09-13 |  |  | Completed | 2 | TECHB-585 |  | Nebula
2021-09-01 | Productivity | UI-Improvement | Template – Selection Column (checkbox), Button Menu | Sampath | 2021-09-14 | 2021-09-20 |  |  | Completed | 5 | TECHB-586 |  | Nebula
2021-09-01 | Productivity | UI-Improvement | Tooltip to be shown for the attached file in the grid column | Sampath | 2021-09-24 | 2021-09-24 |  |  | Completed | 1 | TECHB-593 |  | HCM
2021-09-01 | Productivity | UI-Improvement | CSS & Other extra in print page - VAPT | Sampath | 2021-09-27 | 2021-09-28 |  |  | Completed | 2 | TECHB-594 |  | VAPT
2021-09-01 | Productivity | UI-Improvement | Document Viewer - using Office interop | Sampath | 2021-09-02 | 2021-09-22 |  |  | Completed | 15 | TECHB-595 |  | HCM
2021-09-01 | Productivity | UI-Improvement | Add to Favorites option would be required to be grouped under a Common Group | Sampath | 2021-09-13 | 2021-09-17 |  |  | Cancelled | 5 | TECHB-591 |  | AVN - ERA
Note on K1: Man Days Keep this less than 15. Break up if something goes beyond 15
Note on D39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotfix send - TECH-61386

## Capacity (hidden)
Sprint | Unit | Total Capacity | Leave | Training | Other Efforts | Available Capacity | Load | Load % | Remarks
2021-08-01 | Sampath | 198 | 5 | 110 | 40 | 43 | 88 | 204.7%
2021-08-01 | Rams-Plf | 176 | 25 | 34 | 15 | 102 | 130 | 127.5% | 2 members long leave for their marriage
2021-08-01 | Rams-Infra | 242 | 10 | 88 | 0 | 144 | 192 | 133.3%
2021-08-01 | Rams-ET | 110 | 5 | 22 | 0 | 83 | 105 | 126.5%
2021-09-01 | Sampath | 198 | 5 | 55 | 60 | 78 | 162 | 207.7%
2021-09-01 | Rams-Plf | 210 | 22 | 33 | 15 | 140 | 180 | 128.6% | Venkatesh Marriage
2021-09-01 | Rams-Infra | 231 | 8 | 44 | 20 | 159 | 165 | 103.8%
2021-09-01 | Rams-ET | 105 | 2 | 0 | 15 | 88 | 95 | 108%
2021-10-01 | Rams-Plf | 200 | 8 | 33 | 30 | 129 | 170 | 131.8%
2021-10-01 | Rams-Infra | 220 | 6 | 44 | 20 | 150 | 250 | 166.7%
2021-10-01 | Rams-ET | 80 | 4 | 0 | 20 | 56 | 65 | 116.1%
2021-10-01 | Sampath | 189 | 10 | 63 | 70 | 46 | 120 | 260.9%
2021-11-01 | Rams-Plf | 180 | 9 | 15 | 30 | 126 |  | 0%
2021-11-01 | Rams-Infra | 200 | 10 | 10 | 20 | 160 |  | 0%
2021-11-01 | Rams-ET | 70 | 3 | 0 | 20 | 47 |  | 0%
2021-12-01 | Rams-Plf | 180 | 20 | 15 | 60 | 85 |  | 0%
2021-12-01 | Rams-Infra | 200 | 21 | 10 | 25 | 144 |  | 0%
2021-12-01 | Rams-ET | 70 | 10 | 0 | 20 | 40 |  | 0%

## Other Efforts (hidden)
Sprint | Unit | From Date | To Date | Work Item | Efforts
2021-08-01 | Rams-Plf | 2021-08-01 | 2021-08-31 | Beta adoption support for MDCF generation from platform, side drawer, invoking api from task | 15 | 44433 | 44439 | In Progress
2021-08-01 | Rams-Plf | 2021-08-02 | 2021-08-05 | E5D UT Server - Qlik Sense error | 6
2021-08-01 | Rams-Plf | 2021-07-30 | 2021-08-04 | GSG - Download - Single Quote error in project name | 4
2021-08-01 | Rams-Plf | 2021-08-10 | 2021-08-13 | Cobham - Elastic seach - NLB Token issue - Port conflicits between qlik & elastic | 8
2021-08-01 | Rams-Plf | 2021-08-27 | 2021-08-31 | RIDS - Login page alignment issues (Identified issue in mobile app side with screen resolutions) | 1
2021-08-01 | Rams-Infra | 2021-08-03 | 2021-08-09 | Mobile Gatepass - Print Error | 5
2021-08-01 | Rams-Infra | 2021-08-09 | 2021-08-31 | Schediner Bulk Report - Performance Issue | 4
2021-08-01 | Rams-Infra | 2021-08-09 | 2021-08-13 | Dynamic Grid - Work flow - Hub Issues - Simulation and Verification | 4
2021-08-01 | Sampath | 2021-08-01 | 2021-08-31 | Hub Client Support, Glance, Mhub and Code Generation | 40
2021-09-01 | Sampath | 2021-09-01 | 2021-09-30 | Hub Client Support, Glance, Mhub and Code Generation | 40
2021-09-01 | Sampath | 2021-09-01 | 2021-09-30 | MHub Support | 20
2021-09-01 | Rams-Plf | 2021-09-01 | 2021-09-30 | Beta adoption support for MDCF generation from platform, side drawer, invoking api from task | 30
2021-09-01 | Rams-Plf | 2021-09-01 | 2021-09-30 | Infra - L3 Support | 20
2021-09-01 | Rams-Plf | 2021-09-02 | 2021-09-03 | Eagle cements - mHub esclation - deployment issues and menu configuration file issues | 2
2021-09-01 | Rams-Infra | 23/9/2021 | 2021-09-26 | GSG - Support for 0KB files processing and movement to archieve folder | 3
2021-09-01 | Rams-Infra | 20/9/2021 | 2021-09-23 | ERA - JAVA - Dcube report NaN format issues for numeric values (.56 and .00) . Identified as client side issue and moved to Hub team | 3
2021-10-01 | Rams-Plf | 2021-10-01 | 2021-10-31 | HRP - Moving legacy excel based MDCF into platform model - Extended support | 30
2021-10-01 | Rams-Infra | 2021-10-01 | 2021-10-31 | GSG - Support | 20
2021-10-01 | Rams-ET | 2021-10-01 | 2021-10-31 | Ext JS2 - Support | 20
2021-10-01 | Sampath | 2021-10-01 | 2021-10-31 | Hub Client Support, Glance, Mhub and Code Generation | 50
2021-10-01 | Sampath | 2021-10-01 | 2021-10-31 | MHub Support | 20
2021-11-01 | Rams-Plf | 2021-11-01 | 2021-11-30 | HRP - Moving legacy excel based MDCF into platform model - Extended support | 30
2021-11-01 | Rams-Plf | 2021-11-01 | 2021-11-30 | ERP - Beta adoption support for GQL modeling capablities | 30
2021-11-01 | Rams-Infra | 2021-11-01 | 2021-11-30 | GSG - Support | 20
2021-11-01 | Rams-ET | 2021-11-01 | 2021-11-30 | Ext JS2 - Support | 20
2021-12-01 | Rams-Plf | 2021-11-01 | 2021-11-30 | HRP - Moving legacy excel based MDCF into platform model - Extended support | 15
2021-12-01 | Rams-Plf | 2021-11-01 | 2021-11-30 | ERP - Beta adoption support for GQL modeling capablities | 45
2021-12-01 | Rams-Infra | 2021-11-01 | 2021-11-30 | GSG - Support | 25
2021-12-01 | Rams-ET | 2021-11-01 | 2021-11-30 | Ext JS2 - Support | 20

## Sheet1
| Installation Mode | Topshelf | Quartz
MDCF | Tenantwise | Y | Y
InBox Monitor | Tenantwise | Y | N
Workflow Mailer | Single | Y
Reporting | Single