## Platform-Design
S No | Work Item | Actioner | Target Date | Status | Remarks
1 | Creating Customer, Project, User mapping | Vijay |  | VD - Complete
2 | Create / Manage Process, Component, Activity and User Interface. User Mapping at component level | Vijay |  | VD - Complete
3 | Data Dictionary - Glossary Definition with translate glossary (for multi-language) | Vijay |  | VD - In Progress
4 | Document Generation and User Mapping | Vijay |  | VD - In Progress
5 | Download Work Request | Vijay |  | VD - Yet to Start
6 | Setup UI Preference | Rams |  | KT pending
7 | Layout Designer - Modern approach with drag and drop (end-to-end flow for one real time application screen) | Vijay |  | VD - In Progress
8 | Layout Specification - Classic approach - Usability and enhancement over current specify layout screen (end-to-end flow for one real time application screen) | Vijay |  | VD - In Progress
9 | iRule - KT session of current capability | Alice |  | KT pending
10 | Revised iRule visual design | Vijay |  | VD - Yet to Start
11 | Classic state definition | Rams |  | KT pending
12 | Manage action screen | Rams |  | KT pending
13 | Publication, Subscription and Resolve Links | Vijay |  | VD - In Progress
14 | Maintain requirements rule groups, rule and errors | Rams |  | KT pending
15 | Specify Workflow Inputs | Rams |  | KT pending
16 | Elastic search query mapping | Rams |  | KT pending
17 | Solr query mapping | Rams |  | KT pending
18 | Preview Maintenance - Section and Control Movement | Rams |  | KT pending
18 | Publish Work Request | Vijay
19 | Download ECR | Rams |  | KT pending
20 | Setup Design Preferences | Rams |  | KT pending
21 | Maintain Business Terms | Rams |  | KT pending
22 | Manage Hidden View | Rams |  | KT pending
23 | Pattern Based Service Generation | Rams |  | KT pending
24 | Service Refinements | Rams |  | KT pending
25 | Design Service | Rams |  | KT pending
26 | Design error definition with multi-language translation capability | Rams |  | KT pending
27 | Workflow Incorporation in design | Rams |  | KT pending
28 | Offline Query Modeling | Rams |  | KT pending
29 | UDS query mapping to task | Rams |  | KT pending
30 | API mapping to task | Rams |  | KT pending
31 | Specify MDCF templates | Rams |  | KT pending
18 | Design Maintenance - BT Synonym, BT updates | Rams |  | KT pending
32 | Publish ECR | Rams |  | KT pending
33 | Initiate code generation and view status | Rams |  | KT pending

## iEDK-Design
S No | Work Item | Actioner | Target Date | Status | Remarks
1 | iEDK- KT session of current capability | Alice |  | KT pending